## Release version
Release Notes
Date | Edit by | Change log | Comments
2020-03-18 | All | Initial release
2020-05-04 | All | 1. RMN/RTN/MMN 2. Updated CSTL and schedule version.
2020-05-08 | All | 1. Updated RMN/ RTN
2020-05-20 | All | Updated Schedule version
2020-06-02 | All | Updated Schedule version
2020-06-04 | All | Updated RTS and RTO date to 2021/3/30
2020-07-20 | All | update EAC L/T from 11 --> 14 which based on the latest regulatory rule.
2020-07-23 | All | Update RMN/RTN/MMN - PCR# 8535
2020-07-30 | Raura | Remove Zambia from P-RTS scope, due to certification & Label owner change from Compal to local distributor
2020-08-12 | Monica | Update NRCS lead time from 120 to 134 days
2020-09-09 | Raura/Renee | 1. Update Malaysia certification's start date postpone that ready date from CE RF report (2021/1/25) to CB report (2021/2/1). 2. Update cert target for Serbia, Ukraine, Belarus/Kazakhstan/Russian, Uzbekistan, Moldova because CE DoC Target updating which considring 62368-1, no addition PRTS country adding for safety portion
2020-10-08 | Stella | Update the label impact content for Safety
2020-10-30 | Stella | Add status supplement for CE report.
2020-11-05 | Stella | 1. Safety/EMC/Green schedule update based on contingency plan start from DVT2. 2. Update Combine schedule page (Add column for target date of DVT2) 3. Update P-RTS page (Add column for target date of DVT2)
2020-11-06 | Miya | RF change as below items 1. Update Combine schedule page (Add column for target date of DVT2) 2. Update P-RTS page (Add column for target date of DVT2), Taiwan is P-RTS
2020-11-06 | Renee | 1. Add Serbia, Uzbekistan, Moldova into P-RTS. 2. Update P-RTS target date for Ukraine and Belarus/Kazakhstan/Russian.
2020-11-09 | Miya | 1. Add more Label impact description for China (NAL-WWAN), Philippines (NTC-WWAN) and Mexico (IFETEL-RFID) 2. Update PRTS country summary (WWAN add Philippines and Brazil) 3. Argentina change into RTS
2020-11-19 | Stella | RF reg. engineer changed to Wan Liu.
2020-11-25 | Ian | Pull in the submitted date of CE, BSMI, EMC_KC and Vietnam EMC from 1/19 to 12/14
| Renee | Uzbekistan back into RTS due CE pull in submitted date to 12/14.
| Wan | Reschedule, since EMC report will delay, lead to SDOC complete lately, 11/16 change to 12/14, and will cause PRTS and label impact, combined schedule and Post-RTS sheet will update latley.
2020-12-03 | Tim | 1. CEL status turned DONE. 2. Added Ukraine EcoDesign certification column.
2020-12-10 | Wan | Lebanon lead time chage to 2021/9/11
2020-12-14 | Stella | CB (950) Done
2020-12-24 | Wan | RFID Module: Canada done RFID WW Approval: Belize, Venezuela done
2020-12-30 | Wan | RFID Module: Taiwan, Oman, UAE, Botswana, Singapore, Lao done RFID WW Approval: Belarus done
2021-01-07 | Wan | add Mexcio PCR 1003394 scheduel
2021-01-14 | Renee Wan | 1. Safety KC Done 2. RF Reg cert done: Antigua & Barbuda (RFID), Bahamas (RFID), Costa Rica (RFID), Uruguay (RFID), Egypt (RFID), Chile cert, Fiji (RFID) RF Reg RFID impact: Cambodia, Guyana, Lebanon, Zimbabwe
2021-01-21 | Wan | RF Reg RFID cert done: Bahrain, Mongolia, Panama, Serbia, Tunisia, Malaysia, Papua New Guinea, Paraguay, Dominica,Grenada RF system level done: Korea SAR, USIM report done
2021-01-26 | Renee Wan | 1. CB (62368-1) Done 2. RF Reg cert. done: China SRRC WWAN, Kuwait (RFID), Tanzani (RFID), Suriname (RFID) done
2021-02-02 | Renee | N-mark (62368-1) Done
2021-02-04 | Wan | RF Reg cert. done: Japan, FCC VOC, Canada cert. China SRRC (WLAN), Cote D'ivoire (RFID), Eswatini (RFID) done,
2021-02-08 | walter | JAPAN (VCCI) Done Taiwan (BSMI) Done South Korea (EMC-KC certificate) Done
2021-02-18 | Wan | RF Reg cert. done: Azerbaijan, India (Taiwan) (RFID) done, Thailand, Senegal (RFID) done
2021-02-18 | Alfor | Ukraine ECO Design and USA E-STAR trun Done.
2021-02-18 | Renee | China CCC done
2021-02-24 | Alfor | ENV0379/ DOE/ BCS/ NRCan/ China CEL/ EPEAT turn Done.
2021-02-25 | Renee | Mexico NOM done
2021-02-25 | Wan | RF Reg cert. done: Malawi (RFID), Saint Kitts and Nevis (RFID), Philippines, Morocco, Korea (RFID), FCC grant, FCC (RFID) grant, Peru, Mexico (NOM), Solomon Islands (RFID) Added Saudi Arabia certification
2021-03-02 | Renee | Israel package has been provided to Dell RCE
2021-03-03 | Alfor | UAE RoHS and EAEU RoHS turn Done.
2021-03-04 | Wan | RF Reg cert. done: Bolivia (RFID), Haiti (RFID), Nigeria done
2021-03-10 | Renee | UAE LVE, Serbia, Moldova and India BIS are done
2021-03-11 | Wan | RF Reg cert. done: Dominican Republic (RFID), Malaysia, Argentina,South Africa (RFID)
2021-03-15 | Wan | India(COO:China) RFID SKU cert. is on hold by WPC.
2021-03-17 | Alfor | Vietnam MEPS turn Done.
2021-03-18 | Renee | GS and South Africa_NRCS are done
2021-03-18 | Wan | RF Reg cert. done: Jordan RFID+WLAN, Cambodia Taiwan (RFID)
2021-03-19 | Wan | Zimbabwe (RFID) Done
2021-03-25 | Alyssa | TCO Gen8 done
2021-03-25 | Renee | US/Canada and Uzbekistan certificates are done
2021-03-25 | Wan | RF Reg cert. done: Nicaragua (RFID), Moldova (RFID)
2021-03-26 | Wan | update RTS/RTO to 4/19
2021-03-29 | Monica H. | RF Reg cert. done: Saudi Arabia (CITC)
2021-03-31 | Monica H. | RF Reg cert. done: Ecuador
2021-04-01 | Monica H. | RF Reg cert. done: Saint Lucia (RFID)
2021-04-15 | Monica H. | RF Reg cert. done: Guyana (RFID) Chinal NAL will be postpone to 4/19 Jordon will be postpone to 4/30
2021-04-15 | Renee | EAC is done and back to RTS scope
2021-04-23 | Monica H. | China NAL cert. done
2021-04-26 | Alfor Liao | Updated 34th ESPL CECP/ 32th GPL CEC schedule and status
2021-04-28 | Renee | Ukraine is done
2021-04-28 | Monica H. | Jordan target date maybe postpone to 5/14
2021-05-06 | Monica H. | Jordan: comfirm the marketing name of certificate Brazil: ETA will be updated to 5/17
2021-05-13 | Monica H. | Brazil: cert done by 5/11 Jordan: update ETA 5/21
2021-05-20 | Alfor | China CEC status and RDOC turn Done
2021-05-20 | Monica H. | Jordan: update ETA 5/31 (因本周剛結束齋戒月開始審閱,故延後取證日)
2021-05-26 | Monica H. | Mexico (system): update ETA to 7/16
2021-06-03 | Monica H. | Jordan: cert done
2021-06-15 | Monica H. | Mexico (system): update ETA to 8/31
2021-06-23 | Monica H. | India (RFID): cert. done
2021-06-30 | Alfor | TGM complete
2021-08-24 | Monica H. | Lebanon (RFID): cert. done Mexico (System): update IFT certification status

## Post-RTS
P-RTS country (Mandatory): | [5 empty] | Before↓ | After↓
Project | RTS | Regulatory | Country | Certificate | Lead Time | Schedule (DVT1) | Schedule (DVT2) | Remark | Category | Labeling impact
Carnoustie | 2021-04-19 | RF | Mexico (system) | IFETEL | 84 |  | 2021-08-31 | NOM cert. done + 12wks | Host | No (IFT ID can put on DELL sell website)
2021-04-19
Carnoustie | 2021-04-19 | RF | Lebanon (RFID) | TRA/MoT | 271 | 44362 | 2021-09-24 | CE EMC ready (2020/12/14)+ 39wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | India (RFID) | DoT (China) | 84 | 44221 | 2021-06-23 | CE EMC ready (2020/12/14)+ 12wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Jordan (WWAN) | TRC (RTN) | 56 | 2021-03-09 | 2021-06-03 | CE DOC ready (2021/2/8) + 8wks | Host_WWAN | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Brazil (system) | ANATEL | 154 | 2021-05-03 | 2021-05-11 | Sample ready on 2020/11/30 + 22wks | Host | Yes
Carnoustie | 2021-04-19 | Safety | Ukraine | TEC+NSoC+RoHS | 70 | 2021-06-07 | 2021-06-07 | Consider New RFID Impacted by CE EMC of DVT 2 contingency plan. | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | RF | China (WWAN) | NAL | 116 | 2021-03-26 | 2021-04-29 | Sample ready on 2020/11/30 + 16.6wks China Holiday:2/11~2/17 | Host_WWAN | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May June Block.)
Carnoustie | 2021-04-19 | RF | Ecuador (system) | ARCOTEL | 56 | 2021-06-14 | 2021-04-20 | Wait for FCC grant on 3/30 + 8wks | Host | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Guyana (RFID) | PUC | 168 | 2021-10-04 | 2021-10-04 | Wait for FCC grant on 3/30 + 24wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Mexico (RFID) | IFETEL | 102 | 2021-03-12 | 2021-03-12 | CE EMC ready (2020/12/14)+ 15wks | RFID | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May Block.)
Carnoustie | 2021-04-19 | RF | Saudi Arabia | CITC | 42 | 2021-03-08 | 2021-04-22 | 2021/3/5+ 6wks Back to RTS and certificate done | Host_WWAN | Yes (e-label)
Carnoustie | 2021-04-19 | RF | Saint Lucia (RFID) | NTRC | 126 | 2021-04-19 | 2021-04-19 | CE EMC ready (2020/12/14)+ 18wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Moldova (RFID) | DoC | 112 | 2021-04-05 | 2021-04-05 | CE EMC ready (2020/12/14)+ 16wks Back to RTS and certificate done | RFID | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | RF | Nicaragua (RFID) | TELCOR | 113 | 2021-04-06 | 2021-04-06 | CE EMC ready (2020/12/14)+ 16wks Back to RTS and certificate done | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Zimbabwe (RFID) | POTRAZ | 113 | 2021-02-08 | 2021-04-06 | CE EMC ready (2020/12/14)+ 16.5wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Jordan (WLAN) | TRC (RTN) | 56 | 2021-03-09 | 2021-04-05 | CE DOC ready (2021/2/8) + 8wks Back to RTS and certificate done | Host_WLAN | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Cambodia(RFID) | MPTC | 73 |  | 2021-07-01 | CE EMC ready (2020/12/14)+ 10.5wks Back to RTS and certificate done | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Argentina (RFID) | ENACOM | 133 | 2021-03-29 | 2021-03-29 | Sample ready on 2020/11/16 + 19wks Back to RTS and certificate done Stay with May Block due to BOM lock | RFID | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May Block.)
Carnoustie | 2021-04-19 | RF | Dominican Republic (RFID) | INDOTEL | 70 | 44375 | 2021-06-08 | Wait for FCC grant on 3/30 + 10wks Back to RTS and certificate done | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | South Africa (RFID) | ICASA | 133 | 44312 | 2021-04-26 | CE EMC ready (2020/12/14)+ 19wks Back to RTS and certificate done | RFID | Yes
Carnoustie | 2021-04-19 | RF | Haiti (RFID) | CONATEL | 140 | 2021-05-03 | 2021-05-03 | CE EMC ready (2020/12/14)+ 20wks Back to RTS and certificate done | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Nigeria (system) | NCC | 112 | 2021-05-17 | 2021-05-31 | CE SAR ready (2021/2/8) + 16wks Back to RTS and certificate done | Host | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Taiwan (WWAN) | NCC | 35 | 2021-03-29 | 2021-03-15 | BSMI ready (2021/3/1)+ 5wks Back to RTS and certificate done Stay with May Block due to BOM lock | Host_WWAN | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May Block.)
Carnoustie | 2021-04-19 | RF | Morocco (system) | ANRT | 28 | 2020-03-08 | 2021-03-08 | CE DOC (2/8)+4wks Back to RTS and certificate done | Host | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May Block.)
Carnoustie | 2021-04-19 | RF | Philippines(WWAN) | NTC | 42 | 2021-03-08 | 2021-03-22 | CE DOC (2/8) + 6wks Back to RTS and certificate done | Host_WWAN | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May Block.)
Carnoustie | 2021-04-19 | RF | Solomon Islands (RFID) | TCSI | 84 | 2021-03-08 | 2020-12-28 | Wait for local gov. revise standard Back to RTS and certificate done | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Azerbaijan (system) | ARRVITN | 56 | 2021-04-19 | 2021-04-05 | CE DOC ready (2020/2/8)+8wks Back to RTS and certificate done | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | RF | Thailand (WWAN) | Class B | 42 | 2021-03-08 | 2021-03-08 | CE EMC ready (2021/2/1))+ 6wks Back to RTS and certificate done Stay with May Block due to BOM lock | Host_WWAN | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May Block.)
Carnoustie | 2021-04-19 | RF | Bahamas (RFID) | URCA | 56 | 2021-06-14 | 2021-03-02 | Wait for FCC grant on 3/30 + 8wks Back to RTS and certificate done | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Paraguay (RFID) | CONATEL | 113 | 2021-04-06 | 2021-02-01 | CE EMC ready (2020/12/14)+ 16wks, Back to RTS and certificate done | RFID | Yes (RFID antenna)
Carnoustie | 2021-04-19 | RF | Argentina | ENACOM | 133 | 2021-03-29 | 2021-03-29 | Sample ready on 2020/11/16 + 19wks | Host | Yes (Label impact, over Label turn A date 2021/2/26, cannot meet RTS. Expect label update in April or May Block.)
Carnoustie | 2021-04-19 | RF | Chile | SUBTEL | 112 | 2021-04-05 | 2021-02-08 | Sample ready on 2020/11/16+ 16wks | Host | N/A (no label requirement), no RSE test, move to RTS scope
Carnoustie | 2021-04-19 | Safety | Uzbekistan | Uzbek | 49 | 2021-03-29 | 2021-03-29 | Impacted by CE EMC of DVT 2 contingency plan. Back to RTS | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | RF | Zambia | ZICTA | 70 |  |  | Zambia own by local distributor | Host | Yes
Carnoustie | 2021-04-19 | RF | Israel (RFID) | MoC | 119 | 2021-04-12 | 2021-03-08 | CE EMC ready (2020/12/14)+ 17wks Back to RTS and certificate done | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | Safety | India | BIS | 0 | 0 | 0 | Back to RTS and certificate done | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | Safety | Serbia | Kvatet | 0 | 0 | 0 | Back to RTS and certificate done | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | Safety | Moldova | INSM | 0 | 2020-10-05 | 2020-10-05 | Back to RTS and certificate done | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | Safety | South Africa | NRCS | 134 | 2021-04-27 | 2021-04-27 | Back to RTS and certificate done | Host | N/A (only has module label)
Carnoustie | 2021-04-19 | Safety | Armenia/Belarus/Kazakhstan/Russian/Kyrgyzstan | CU | 98 | 2021-05-17 | 2021-05-17 | Back to RTS and certificate done | Host | No (can be ready first, set restriction until certification ready)
P-RTS Country (Voluntary):
Project | RTS | Regulatory | Country | Certificate | Lead Time | Schedule (DVT1) | Schedule (DVT2) | Remark
Carnoustie | 2021-03-30 | Green | Taiwan | TGM | 100 | 2021-07-08 | Done | Volumtary Certification, not RTS gating item. Need to confirm BSMI certificate and service manual (RTS) + TWN/EDF(100 days)
Carnoustie | 2021-03-30 | Green | China | CEC | -- | Per ESPL wish list to do | Done | 2021/5/20 done
Carnoustie | 2021-03-30 | Green | China | CECP | -- | Per ESPL wish list to do | 2021-04-18 | For China purchase case
Aligned with GOE, Label is post-FRC item, but can be RTS scope
Project | RTS | Regulatory | Country | Certificate | Lead Time | Schedule (DVT1) | Schedule (DVT2) | Remark | Category | Labeling impact
Formulas:
After↓ = [RTS]+[Lead Time]

## Combine Schedule
PRTS country summary
RFQ PRTS country (Mandatory) | System: Azerbaijan, Brazil, Chile, Ecuador, Jordan(move to WWAN SKU), Mexico(IFT), Morocco, Nigeria, Zambia, Ukraine, Armenia/Belarus/Kazakhstan/Russian/Kyrgyzstan, South Africa, India, Moldova, Serbia, Saudi Arabia, Uzbekistan, Mexico RFID SKU: Argentina, Bahamas, Cambodia, Dominican Republic, Guyana, Haiti, Israel, India, Lebanon, Moldova, Mexico, Nicaragua, Paraguay, Saint Lucia, Soloman Islands, South Africa, Zimbabwe WWAN SKU: China(NAL), Philippines, Taiwan, Thailand, Jordan
RFQ PRTS country (Voluntary) | Taiwan (TGM, label impact)
Remark
Carnoustie schedule | [12 empty] | Carnoustie
[13 empty] | DVT1.0 | 2020-10-05 | 2020-10-05
[13 empty] | DVT2.0 | 2021-01-12 | 2021-01-12
[13 empty] | PVT | 2021-03-18 | 2021-03-18
[13 empty] | RFD | 2021-03-24 | 2021-03-24
Marketing model #: Latitude 7320 2-in-1; Latitude 7320-01 2-in-1(China WWAN) | [12 empty] | RTS | 2021-04-19 | 2021-04-19
Regulatory model #: T04H | [12 empty] | RTO | 2021-04-19 | 2021-04-19
Regulatory type. #: T04H001 | [12 empty] | schedule ver. | Carnoustie 13 working MU (42wks)schedule 20200220_a | Carnoustie 13 working MU (42wks)schedule 20200220_a
| RF |  |  |  | Safety |  |  |  | Green |  |  |  | EMC |  |  |  | Certification color code
Country | Certification | Label | Date (DVT1) | Date (DVT2) | Certification | Label | Date (DVT1) | Date (DVT2) | Certification | Label | Date (DVT1) | Date (DVT2) | Certification | Label | Date (DVT1) | Date (DVT2) | Before RFD
Argentina | CNC |  | 2021-03-29 | Done | [12 empty] | Between RFD and RTS
Aruba | DTZ |  | 2021-02-15 | Done | [12 empty] | After RTS, please set restriction
Armenia | PSRC |  | 2021-01-11 | Done | CU | Back Cover |  | Done | EAEU ROHS |  |  | Done |  |  |  |  | After RTO, please set restriction
Australia/ New Zealand | RCM | COO | 2021-01-25 | Done |  |  |  |  | MEPS (out of scope) | N/A | N/A |  | RCM by CE | Back Cover | 2020-12-14 | Done
Antigua and Barbuda | MBT |  | 2021-01-25 | Done
Azerbaijan | ARRVITN |  | 2021-03-22 | Done
Barbados | TU |  | 2021-01-11 | Done
Bahamas | URCA |  | 2021-06-14 | Done
Bahrain | iGA |  | 2021-01-25 | Done
Belarus | DoC |  | 2021-03-22 | Done | CU | Back Cover | 2021-05-17 | Done | EAEU ROHS |  | 2021-03-02 | Done
Belize | PUC |  | 2021-02-08 | Done
Bolivia | ATT |  | 2021-03-22 | Done
Brazil | ANATEL | IDV | 2021-05-03 | Done
Brunei | AITI-Dell own
Botswana | BOCRA |  | 2021-02-01 | Done
Canada | IC | COO | 2021-02-15 | Done | UL | COO | 2021-03-22 | Done | NRcan BC | PKG | 2021-02-26 | Done
Cambodia | MPTC |  | 2021-01-18 | Done
Chile | SUBTEL |  | 2021-04-05 | Done
China | SRRC | COO | 2021-02-22 | Done | CCC | COO | 2021-02-08 | Done | CEL | PKG | Done | Done
China | NAL | IDV | 2021-03-26 | Done
Colombia | LoNA-Dell own |  |  | Done
Costa Rica | SUTEL |  | 2021-01-18 | Done
Dominican Republic | INDOTEL |  | 2021-06-28 | Done
Dominica | NTRC |  | 2021-03-08 | Done
DR Congo | ARPTC-Dell own
Ecuador | ARCOTEL |  | 2021-06-14 | Done
Egypt | NTRA |  | 2021-02-08 | Done
EU (CE) | CE | COO | 2021-01-25 | Done | CB |  | 2021-02-01 | Done |  |  |  |  | CE | Back Cover | 2020-12-07 | Done
EU (EN301489-1/3/17/19) |  |  | 2020-12-14 | Done | [8 empty] | EN301489-1/3/17/19 |  | 2020-12-14 | Done
EU (EN301489-52) | [12 empty] | EN301489-52 |  | 2020-12-14 | Done
Fiji | TAF |  | 2021-01-29 | Done
Germany |  |  |  |  | GS | COO | 2021-03-22 | Done
Ghana | NCA |  | 2021-02-01 | Done
Grenada | NTRC |  | 2021-02-22 | Done
Guyana | PUC |  | 2021-10-04 | Done
Haiti | CONATEL |  | 2021-05-03 | Done
India | DoT |  | 2021-02-01 | Done | BIS | IDV | 2021-04-19 | Done
Indonesia | SDPPI
Israel | MoC |  | 2021-04-12 | Done | Dell own
Ivory Coast (Cote D'ivoire) | ARTCI |  |  | Done
Jamaica | SMA |  | 2021-02-01 | Done
Japan | MIC | IDV | 2021-02-08 | Done | [8 empty] | VCCI | Back Cover | 2020-12-21 | Done
Jordan | TRC |  | 2021-03-22 | Done
Kazakhstan |  |  |  |  | CU | Back Cover | 2021-05-17 | Done | EAEU ROHS |  | 2021-03-02 | Done
Kenya | CAK
Kiribati | CCK |  | 2021-02-22 | drop by DELL
Korea | USIM |  | 2021-02-08 | Done | KC | COO | 2021-02-01 | Done | KES (out of scope) |  | N/A |  | KCC | COO | 2021-02-22 | Done
Kuwait | MoC |  | 2021-02-23 | Done
Kyrgyzstan |  |  |  |  | CU | Back Cover |  | Done | EAEU ROHS |  |  | Done
Lao, People's Demo, Rep. | MPT |  | 2021-01-25 | Done
Lebanon | TRA/MoT |  | 2021-06-15 | Done
Madagascar | OMERT- Dell own
Malawi | MACRA |  | 2021-02-12 | Done
Malaysia | MCMC | COO | 2021-03-15 | Done
Mauritius | ICTA-Dell own
Mexico (system) | NOM-208/NOM-221 |  |  | Done
Mexico (system) | IFETEL |  | 2021-03-12 | 2021-08-31 | NOM | Back Cover | 2021-02-26 | Done | MEL (out of scope) |  | N/A
Mexico (RFID) | IFETEL |  | 2021-04-05 | Done
Moldova | ANRCETI | IDV (RFID) | 2021-04-05 | Done | INSM |  | 2021-03-29 | Done
Morocco | ANRT | COO | 2021-03-08 | Done
Mongolia | CRC |  | 2021-02-08 | Done
Nepal | NTA
Nicaragua | TELCOR |  | 2021-04-06 | Done
Nigeria | NCC | IDV | 2021-05-17 | Done
Norway |  |  |  |  | Nemko | Back Cover | 2021-02-15 | Done
Oman | TRA |  | 2021-01-25 | Done
Panama | ASEP |  | 2021-02-22 | Done
Pakistan
Papua New Guinea | NICTA |  | 2021-02-01 | Done
Paraguay | CONATEL |  | 2021-04-06 | Done
Peru | MTC |  | 2021-03-08 | Done
Philippines | NTC | IDV | 2021-03-08 | Done
Qatar | ictQATAR-Dell own
Russia - Minsviaz |  |  |  |  | CU | LCD Cover | 2021-05-17 | Done | EAEU ROHS |  | 2021-03-02 | Done
Rwanda | RURA-Dell own
Saint Kitts and Nevis | NTRC |  | 2021-03-08 | Done
Saint Lucia | NTRC |  | 2021-04-19 | Done
Saudi Arabia | CITC |  | 2021-01-25 | Done
Senegal | ARTP |  | 2021-02-22 | Done
Serbia | RATEL |  | 2021-01-29 | Done | Kvatet | COO | 2021-03-29 | Done
Singapore | IDA |  | 2020-12-28 | Done
Swaziland | SPTC |  | 2021-02-08 | Done
Suriname | TAS |  | 2021-02-08 | Done
South Africa | ICASA |  | 2021-04-26 | Done | NRCS |  | 2021-04-27 | Done
Solomon Island | TCSI |  | 2021-03-08 | Done
Sri Lanka | TRCSL-Dell own
Taiwan | NCC |  | 2021-03-29 | Done | EMI OWN |  |  |  | TGM | Carton |  | Done | BSMI | Back Cover | 2021-02-22 | Done
Tanzania | TCRA |  | 2021-02-01 | Done
Thailand SDoC (WLAN SKU) | NBTC |  | 2021-02-15 | Done
Thailand (WWAN SKU) | NBTC | IDV | 2021-03-08 | Done
Trinidad & Tobago | TATT
Tunisia | CERT |  | 2021-02-12 | Done
United States | FCC |  | 2021-03-17 | Done | UL | COO | 2021-03-22 | Done | USA BCS | N/A | 2021-02-26 | Done | FCC report | IDV (Statement) | 2020-12-14 | Done
[9 empty] | USA DOE | N/A | 2021-02-26 | Done
[9 empty] | CEC MEPS (out of scope) | N/A | N/A
UAE | TRA |  | 2021-01-25 | Done | LVE | Sticker in box | 2021-03-22 | Done | UAE ROHS |  | 2021-03-02 | Done
Uganda | UCC-Dell own
Ukraine |  |  |  |  | UKSERT | COO | 2021-06-07 | Done | ECO design |  | 2021-03-10 | Done
Uruguay | URSEC |  | 2021-01-04 | Done
Uzbekistan |  |  |  |  | Uzbek |  | 2021-03-29 | Done
Venezuela | CONATEL |  | 2021-01-18 | Done
Vietnam | RF-EMC (QCVN96) RF (QCVN55) |  | 2021-01-25 | Done |  |  |  |  | MEPS test report |  | 2021-03-29 | Done | Vietnam EMC Report |  | 2021-01-25 | Done
Zambia | ZICTA
Zimbabwe | POTRAZ |  | 2021-03-08 | Done
Green Team Voluntary Approval
Certification/Country | Target Date | Label | Notes
Energy star 8.0 | Done | OS
China/CECP | Per ESPL wish list to do | ESPL COO/ CEL
China/CEC | Per ESPL wish list to do | N/A
Taiwan/TGM | 2021-07-08 | IDV | Not RTS gating item
Brazil/INMETRO | N/A | IDV | Tablet is out of scope.
India BEE star | N/A | IDV | Tablet is out of scope.
TCO Gen.8 | 2021-03-29 | IDV
EPEAT | Done | N/A
Label & User manual trigger date
Label Artwork | target date | Remark
LRF submittal date (RTS -29wks) | 2020-09-28
Draft label AW submittal date (RTS -9wks) | 2021-02-15
Final AW to Dell/RCE review/approve (RFD - 2wks) | 2021-03-10
Locked down date (Label turn A date -3 days) | 2021-03-14 | Dell/RCE approval date
Label turn A (RFD-1wks) | 2021-03-17 | Label vendor completed upload to Agile
Mockment & QSG | target date | Remark
mockument (CB submittal date -2wks) | 2020-10-12 | ODM own
Release DRF to DELL (DVT 1.0 ETA) | 2020-10-05 | ODM own
QSG in English/T-Chinese/ Hebrew (A-rev.) (RFD-6wks or BSMI target date -6wks or Isaral ready date) | 2021-01-11 | Dell Own
Formulas:
RF = [RF, row below]-3

## S&G&E Schedu_DVT2 Start
Carnoustie
Program Status | 1. Carnoustie CSTL v1.0_1 2. Carnoustie 13 schedule_X07a 2. Chinese new year: 2021/2/11-2021/2/16
Regulatory model name | T04H |  | RFD Date: | 2021-03-24 | System CE SAR (excluding WWAN): | 2021-01-11
Regulatory Type name | T04H001 |  | ODM RTS Date: | 2021-04-19 | System CE SAR(including WWAN): | 2021-01-25
Marketing model name (for China WLAN) (for China WWAN) | Latitude 7320 Detachable Latitude 7320-01 Detachable |  | RTO Date: | 2021-04-19 | Korea SAR: | 2021-02-08
Marketing model name (for WW) | Latitude 7320 Detachable |  | Safety Engineer: | Renee Chu | QSG Release Date: | 2021-02-10
|  |  | EMC Engineer: | Ian Chien
Project code #: | FDB33 |  | Green Engineer: | Alfor Liao
Testing/ Verifaction | Sample ETA to LKE | Start | End | Comments
EVT1 | 2020-07-15 | 2020-07-15 | 2020-07-29 | TR on 6/17, need to provide report to ME before TR for solution adding
DVT1 | 2020-10-05 | 2020-10-05 | 2020-10-26
DVT2 | 2021-01-12 | 2021-01-12 | 2021-02-02 | EMC Critical ship ETA LKE: 2020/12/29
PVT | 2021-03-18 | -- | --
BOM Lock Down Plan | Start | End
BOM lock Down | 2021-02-01 | 2021-02-15
Label Turn A Plan | A00 | A01
Label | 2021-03-17 | TBD
Region | Duration (day) | Submitted Date | Target date | Complete | Status | Owner | RDOC Cert. | RDOC Report
Americas
FCC Report | 7 | 2021-01-25 | 2021-02-01 | Done |  | EMC | N/A | Done
USA/CANADA (UL 62368-1 3ed) | 42 | 2021-02-01 | 2021-03-22 | Done | Upload UL NoA first and still wait for UL CoC (system outage) | Safety | N/A | Done
Mexico (NOM) | 35 | 2021-02-10 | 2021-03-17 | Done |  | Safety | Done | N/A
Brazil (INMETRO) | 49 | -- | N/A |  | Tablet is out of scope. | Green
ENV0379 Report | -- | -- | 2021-03-17 | Done |  | Green | N/A | Done
USA (Energy Star 8.0) | 30 | 2021-03-25 | 2021-03-17 | Done |  | Green | Done | Done
CEC (MEPS) | -- | -- | N/A |  | Tablet is out of scope. | Green
USA (EPEAT-2018) | 28 | 2021-03-25 | 2021-03-17 | Done |  | Green | N/A | Done
USA (BCS/ DOE/ NRCan) | 42 | 2021-02-03 | 2021-03-17 | Done |  | Green | Done | Done
Mexico (MEL) | -- | -- | N/A |  | Tablet is out of MEL scope. | Green
Europe & Middle East
CE Report (EN55022 and EN55032) | 42 | 2020-12-14 | 2021-01-25 | Done |  | EMC | N/A | Done
EN301489 | 49 | 2020-12-14 | 2021-02-01 | Done |  | EMC | N/A | Done
CB (60950-1) | 49 | 2020-10-26 | 2020-12-14 | Done |  | Safety | Done | Done
CB (62368-1 3rd edition) | 84 | 2020-11-09 | 2021-02-01 | Done |  | Safety | Done | Done
NEMKO | 7 | 2021-02-08 | 2021-02-22 | Done |  | Safety | Done | N/A
DELL EMC DoC | 7 | 2021-02-01 | 2021-02-08 |  |  | DELL |  | N/A
Germany (TUVRh-GS or EN62368-1 3ed ) | 42 | 2021-02-01 | 2021-03-22 | Done |  | Safety | Done | Done
UAE RoHS | 42 | 2021-02-02 | 2021-03-16 | Done |  | Green | Done | N/A
UAE (LVE) | 42 | 2021-02-01 | 2021-03-22 | Done | Need to wait CB (62368-1) ready for the submission | Safety | Done | Done
Israel Package |  | -- | 2021-03-17 | Done |  | Safety | N/A | N/A
Serbia (KVALITET) | 56 | 2021-02-08 | 2021-04-07 | Done |  | Safety | Done | N/A
Ukraine (TEC+NSoC+RoHS) | 70 | 2021-03-08 | 2021-06-07 | Done | Consider New RFID | Safety | Done | N/A
Armenia/Belarus/Kazakhstan/Russian/Kyrgyzstan (CU) | 98 | 2021-02-08 | 2021-05-17 | Done |  | Safety | Done | N/A
EAEU RoHS | 42 | 2021-02-02 | 2021-03-16 | Done |  | Green | Done | N/A
Ukraine EcoDesign | 42 | 2021-01-27 | 2021-03-10 | Done |  | Green | Done | N/A
Uzbekistan | 49 | 2021-02-08 | 2021-03-29 | Done |  | Safety | Done | N/A
Moldova | 56 | 2021-02-08 | 2021-04-07 | Done |  | Safety | Done | N/A
Saudi Arabia (SASO) | DELL Own | -- | 2021-03-17 |  |  | DELL | Done
South Africa (NRCS) | 134 | 2020-12-14 | 2021-04-27 | Done |  | Safety | Done | N/A
Kenya(KEBS) | DELL Own | -- | 2021-03-17 |  |  | DELL
Kuwait (KUKAS) | DELL Own | -- | 2021-03-17 |  |  | DELL
Nigeria(SONCAP) | DELL Own | -- | 2021-03-17 |  |  | DELL
Algeria | DELL Own | -- | 2021-03-17 |  |  | DELL
Ethiopia | DELL Own | -- | 2021-03-17 |  |  | DELL
Tanzania | DELL Own | -- | 2021-03-17 |  |  | DELL
Uganda | DELL Own | -- | 2021-03-17 |  |  | DELL
TCO Gen8 | 28 | 2021-03-21 | 2021-04-18 | Done |  | Green | Done | Done
Asia Pacific (APJ)
JAPAN (VCCI) | 14 | 2021-01-25 | 2021-02-08 | Done |  | EMC | N/A | Done
Taiwan (BSMI) | 42 | 2020-12-14 | 2021-02-08 | Done |  | EMC/Safety | Done | Done
Taiwan (TGM) | 100 | 2021-04-19 | 2021-07-28 | Done | Volumtary Certification, not RTS gating item. Need to confirm BSMI certificate and service manual (RTS) + TWN/EDF(100 days) | Green |  | N/A
China (CCC) | 42 | 2020-12-14 | 2021-02-08 | Done |  | Safety | Done | Done
China (CEL) | 30 | 2021-01-19 | 2021-02-18 | Done |  | Green | Done | Done
China (CECP) | -- | -- | 2021-04-18 | Done | 34th ESPL/ 32th GPL | Green | Done | Done
China (CEC) | -- | -- | 2021-05-16 | Done | 34th ESPL/ 32th GPL | Green |  | N/A
India (BIS) | 98 | 2021-01-11 | 2021-04-19 | Done | Schedule is based on Battery pack BIS ready before 2021/1/11 | Safety | Done | Done
India (BEE Star) | -- | -- | N/A |  |  | Green
South Korea (Safety-KC) | 35 | 2020-12-14 | 2021-02-01 | Done |  | Safety | Done | N/A
South Korea (EMC-KC report) | 42 | 2020-12-14 | 2021-01-25 | Done |  | EMC | N/A | Done
South Korea (EMC-KC certificate) | 14 | 2021-02-08 | 2021-03-01 | Done | Initial cert need to wait KC-SAR done | EMC | Done | N/A
South Korea (eStandby) | 30 | -- | N/A |  | Tablet is out of scope. | Green
South Korea (Eco-Label) | DELL Own | -- | N/A |  |  | DELL
Vietnam EMC Report | 42 | 2020-12-14 | 2021-01-25 | Done |  | EMC | N/A | Done
Vietnam MEPS Report | 56 | 2021-02-21 | 2021-04-18 | Done |  | Green | N/A | Done
Australia/New Zealand
MEPS | 30 | -- | N/A |  |  | Green
RCM Report | 7 | 2021-01-25 | 2021-02-01 | Done |  | EMC | N/A | Done
This schedule is base on :
System and adapter sample arrive on |  |  | 2020-10-05 |  | Carnoustie battery Safety NOA |  | BYD | SMP | SWD
DELL LoA |  |  | 2020-10-05 |  |  | UL2054/UL62368 | 2020-10-19 | 2020-10-19 | 2020-10-19
DELL EMC DoC ready on (English) |  |  | 2021-02-01 |  |  | CB60950/CB62133/CB62368 | 2020-10-19 | 2020-10-19 | 2020-10-19
DELL EN62311 DoC and RF related Documents |  |  | 2021-02-01 |  |  | CE | 2020-10-26 | 2020-10-26 | N/A
User's manual and rating label in English |  |  | 2020-10-05 |  |  | TUV60690/TUV62368 | 2020-10-26 | 2020-10-26 | 2020-10-26
User's manual with Other language T-Chinese, S-Chienese, Russian, Hebrew, Korea, Spanish, Serbian, Portuguese |  |  | 2020-10-26 |  |  | PSE | 2020-10-26 | 2020-10-26 | 2020-10-20
Key part cert. & report ready (ex. Adapter/Batterypack…etc): CB |  |  | 2020-10-19 |  |  | TISI | 2020-10-19 | 2020-10-19 | Done
Key part cert. & report ready (ex. Adapter/Batterypack…etc): Others |  |  | 2020-12-14 |  |  | KC | 2020-11-02 | 2020-11-02 | 2020-11-22
Acoustic report ready |  |  | N/A |  |  | GOST | 2020-11-02 | 2020-11-02 | 2020-11-02
BSMI授權進口書(if needed) |  |  | 2021-02-08 |  |  | BSMI | 2020-11-02 | 2020-11-15 | 2020-11-02
[6 empty] | GB31241 | 2020-11-09 | 2020-11-09 | 2020-11-09
Certificate color code | [5 empty] | VN IEC 62133 | 2020-11-09 | 2020-11-09 | 2020-11-09
before RFD | [5 empty] | BIS (62133-2:2017) | 2021-01-11 | 2021-01-11 | 2021-01-11
Between RFD and RTS
After RTS before RTO, please set restriction
After RTO, please set restriction
Completed
Formulas:
Start = [FDB33]
Start = [Green Engineer:]-[FDB33]
Green Engineer: = [Start]+14
Green Engineer: = [Start]+[FDB33]
FDB33 = [Start]-14
Note on I67: Liao. Alfor (LKE): 06/30 Certification still not issued

## RF Schedule DVT2
Carnoustie (Portable Computer - Tablet) | [5 empty] | Schedule ver. Carnoustie 13 schedule_X07a | [8 empty] | Antenna Filing |  |  | NCC Photo Filing (after RTO) |  | AX210_FCC/CE report ready |  | 2020-12-31 | 12/4~2021/2/5
CG | SPT | Min. ant-to-body distance | NB: 200mm TB: 2.1mm | RMN | T04H | DVT1.0 Sample ETA | 2020-10-05 | Safety CB Report/Cert | 2021-02-01 | Label Turn A | 2021-03-17 |  |  |  | Module | Antenna Cycle | Actual Submitted Date | Antenna Cycle | Actual Submitted Date | AX210_JP/KR/China |  | 2021-02-05
Project Code | (APR)FDB33 | RF module | WLAN/BT 1. AX201D2W RFID: DWRFID2002 WWAN: T77W968 (DW5821e, CAT16, Darwin 1.0)(FCC ID:MCLT77W968-D10/IC ID:2878D-T77W968) | RTN | T04H001 | DVT1.0 Regulatory Sample for RFID (+6wks) | 2020-11-16 | EMC EN 301489 | 2021-02-01 | RFD Date | 2021-03-24 |  |  |  | AX201D2W | 1/4~2/8 | 2020-12-31 |  |  | AX210_Malaysia |  | 2021-04-08 | 2/25~4/8
RF RD | Lee. IvanSH |  |  | MMN-WLAN | Latitude 7320 Detachable | DVT1.0 Regulatory Sample for WLAN (+6wks) | 2020-11-20 | BSMI Report/Cert | 2021-02-08 | RTS Date | 2021-04-19 |  |  |  | T77W968 | Jan. 2021 | Jan. 2021 | 2021/3/1~2021/4/21
RF Lab | BV-ADT |  |  | MMN-WWAN | Latitude 7320-01 Detachable | DVT1.0 Regulatory Sample for WWAN (+8wks) | 2020-11-30 | A Rev Driver |  | RTO Date | 2021-04-19
[6 empty] | DVT1.1 Sample ETA | 2020-11-09 | DVT1.1 Regulatory Sample (+6wks) | 2020-11-30 | CE DOC | 2021-02-08
Country | Type Approval | Module | Start Date | L/T | Target Date | Status Summary | Actual Start | Actual Completion | Reg. Model Name | Label Requirement | RDOC Cert. | RDOC Report | Label impact | proto | proto-keypad | NRE | Actual $
SAR | [19 empty] | Antenna information (Slot)
EU | EN 50566/EN 62209 | AX201 | 2020-11-20 | 56 | 2021-01-15 | 12/29 provided draft report 12/23 finished test ,preparing report 11/26, 12/3,10,16 under testing 11/24 got power spec ,under testing | 2020-11-20 | 2021-01-05 | RMN |  |  | V (2021/5/6) |  | 4 | 1 |  | 20160 |  |  | SKU | Vendor | Main | Aux
|  | T77W968 | 2020-11-30 | 56 | 2021-01-25 | 12/23,29, 1/6,13 under testing 12/18 got WNC antenna report ,under testing 12/07,16 under testing ,waiting antenna reports 12/04 got sample ,function check waiting for sample | 2020-12-04 | 2021-01-20 | RMN |  |  | V (2021/5/6) |  | 8 | 1 |  | 28700 |  |  | WWAN (LTE) | HongBo | 260-24334 (DC33002GR0L) | 260-24335 (DC33002GR1L)
Australia | AS/NZS 2772.2:2011 | AX201 | 2020-11-20 | 56 | 2021-01-15 | same as CE | 2020-11-20 | 2021-01-05 | RMN |  |  | V (2021/5/6) |  | use CE | use CE |  | 1400 |  |  | WWAN (LTE) | WNC | 81ELAW15.G18 (DC33002HP2L) | 81ELAW15.G19 (DC33002HP3L)
|  | T77W968 | 2020-11-30 | 56 | 2021-01-25 | same as CE | 2020-12-04 | 2021-01-20 | RMN |  |  | V (2021/5/6) |  | use CE | use CE |  | 1400 |  |  | WLAN_only | HongBo | 260-24336 (DC33002GR2L)
US/Canada | SAR+Testing 1/1問Intel測試結果 | AX201 | 2020-11-27 | 49 | 2021-01-15 | 11/24-Intel Report Date 1/15 | 2020-11-24 | 2021-01-20 | RMN |  | V (2021/5/6) | V (2021/5/6)
| Voc | AX201 | 2021-01-15 | 28 | 2021-02-12 | 3/3 grant date change to 2/22 ready | 2021-01-20 | 2021-02-23 | [11 empty] | WLAN_only | WNC | 81ELAW15.G51 (DC33002HP0L)
| SAR | T77W968 | 2020-11-30 | 63 | 2021-02-01 | 1/26 final report 1/20 preparing report 12/23,29, 1/6,13 under testing 12/18 got WNC antenna report ,under testing 12/04,09,16 under testing ,but waiting antenna report 12/03 function check 12/02 got sample waiting for sample ,(需確認intel 報告ready 時間) | 2020-12-02 | 2021-01-26 | RMN |  |  | V (2021/5/6) |  | 8 | 1 |  | 71400 |  |  | NFC Antenna | HongBo | 260-24337 (DC33002GR3L)
| Review-Voc |  | 2021-02-01 | 21 | 2021-02-22 | 1/28 in process 1/26 submit documents | 2021-01-26 | 2021-02-02 | RMN | [7 empty] | 5985 |  |  | NFC Antenna | WNC | 81EABH15.G01 (DC33002HP1L)
Korea | KC SAR | AX201 | 2020-11-20 | 70 | 2021-01-29 | 12/18 got WWAN report ,no need WIFI SKU sar reports to submit (because the wifi antenna location is the same with WWAN SKU) 12/02,09,16 wait for test 11/26 transfer sample to local lab | 2020-11-20 | 2020-12-18 | RTN |  |  | V (2021/5/6) |  | 1 |  |  | 11025
|  | T77W968 | 2020-11-30 | 70 | 2021-02-08 | 01/06,13 wait for test 12/29 wait for test, would be tested by 8-Jan. 12/16,23 wait for test 12/09 sample in transit 12/03 function check 12/02 got sample waiting for sample | 2020-12-02 | 2021-01-21 | RTN |  |  | V (2021/5/6) |  | 3 |  |  | 9975 | 收到報告結案
Japan | SAR | T77W968+AX201 | 2020-11-30 | 56 | 2021-01-25 | 1/20 final report , wait for cert 12/23,29, 1/6,13 under testing 12/18 got WNC antenna report ,under testing 12/04, 10,16 under testing ,but waiting antenna report 12/03 function check 12/02 got sample 11/30 waiting for sample | 2020-12-02 | 2021-01-20 | RTN | (IDV) R: 020-210013 5GHz band (W52,W53): Indoor use only (except communicate to high power radio) | V (2021/5/6) | V (2021/5/6) |  | use CE | use CE |  | 10920
| Review |  | 2021-01-25 | 14 | 2021-02-08 | 1/28 under reviewing 1/20 will be submit on 1/21 | 2021-01-21 | 2021-01-29 | RTN | [7 empty] | 13650
System Approval | [13 empty] | proto | proto-keypad | NRE | Actual $
Argentina | ENACOM | RFID | 2020-11-16 | 133 | 2021-03-29 | 12/23,29, 1/6,13, 20, 27, 2/3,24, 3/4 under review 12/15 under submit 12/14 report confirmed ok 12/09 test done, wait for report 12/02 wait for test 11/19-function check ok ,transfer sample to local lab. | 2020-11-16 | 2021-03-09 | RMN | (IDV) CNC ID: H-25956 | V (2021/5/6) |  |  | 2 |  |  | 7350
Azerbaijan | ARRVITN | All modules | 2021-02-08 | 56 | 2021-04-05 | 02/03 application in process 01/26 application submitted wait for CE DOC push to lab pull in DOC whether in 2days prevent PRTS 1.拿到報告立馬送doc 2.問lab是否可以先送仁寶doc再補件 | 2021-01-26 | 2021-02-08 | RMN |  | V (2021/5/6) | [5 empty] | 4095
Belarus | DoC (CIT+PCP+CDT) | AX201 | 2021-02-08 | 49 | 2021-03-29 | 12/23 wait for final DOC 12/16 wait for DOC 12/09 confirmed OK 12/08 got draft, wait for confirmation 12/02 under review | 2020-12-02 | 2020-12-29 | RMN | (WW) TP Logo | V (2021/5/6) |  |  | 2 | 1 |  | 4620
Brazil | ANATEL Class 2 (CIT+PCP+CEB+CDT) | AX201(+RFID) | 2020-11-20 | 154 | 2021-04-23 | 11/13 drop by Dell |  |  | RMN | (IDV) ANATEL: 01432-20-01643 | V (Date) | [5 empty] | 0
| ANATEL Class 1 (CIT+PCP+CEB+CDT) | AX201+T77W968 (+RFID) | 2020-11-30 | 154 | 2021-05-03 | 5/5 under review, ETA will be updated to 5/17. 4/28 under review, OCD will ask for DELL Brazil help to check with ANATEL on status, not sure if will receive certificate on time 04/07, 14, 21 under ANATEL review 03/31 under OCD reviewing 03/23 in test 03/10 wait for pending items, new adapter wait for test 03/03 New adapter of HA60NM200 was under shipment. Other testing is done. Lack Differences between model letter 02/03,17,24 under testing, wait for sign letters 01/20,27 under testing 01/06,13 wait for test 12/18-1/04 Holiday 12/16 sample arrived 12/09 in transit 12/07 function check finished ,sample transfer to local lab 12/03 function check 12/02 got sample Adapter for 60W -DVT1 sample Delta: 12 -DVT2 early sample demand before 10/12 Liteon: 24 Chicony: 24 2020/7/30: Ask additional adapter sample, PJE inform 40W & 65W ok, 60W adapter need checking (ETA: 10/E, EMC recommend use Early sample for Liteon/ Chicony, and hightlight to CT if testing fail) | 2020-12-02 | 2021-05-11 | RMN | (IDV) ANATEL: 01431-20-01643 | V (2021/5/11) |  |  | 14 | 2 |  | 83475
Chile | SUBTEL | AX201 | 2020-11-30 | 70 | 2021-02-08 | 12/23,29, 1/6 in process 12/16 under submit 12/14 application submitted 12/9 wait for RFID report (report description) 12/2 got comment on photo, wait for RFID report No testing required (by submit RF module reports) | 2020-11-30 | 2021-01-14 | RMN |  | V (2021/5/6) | [5 empty] | 2100
|  |  | 2021-01-15 | 84 | 2021-04-09 |  |  |  | RMN
China | SRRC (WLAN) | AX201 | 2020-11-20 | 10 | 2020-11-30 | 12/23 under submit ,waiting approval, impact target time from 2/12 to 3/5 12/18 wait for signed doc 12/08 application rejected, wait for signed doc 12/02 application submitted 11/19 lack antenna report to preparing signing letter 11/16-got sample from RD (文件&寄樣) | 2020-11-16 | 2020-11-24 | MMN-WLAN | (COO) CMIIT ID: 2021AP0645 | V (2021/5/6) |  |  | 1 |  |  | 3150
|  |  | 2020-11-30 | 39 | 2021-01-08 | 01/13 in test 01/06 wait for test 11/24 -under submit ,waiting for approval (受理&排測) | 2020-11-24 | 2021-02-03
|  |  | 2021-01-08 | 21 | 2021-01-29 | 01/20 report upload and under review (測試) | 2021-01-20 | 2021-02-03
|  |  | 2021-01-29 | 35 | 2021-03-05 | 01/27 under review (審理&取證) | 2021-01-27 | 2021-02-03
| SRRC (WWAN) | T77W968+AX201 | 2020-11-30 | 10 | 2020-12-10 | 12/23 under submit ,waiting approval, impact target time from 2/12 to 3/5 12/22 confirmed 加工協議issue 12/08 application rejected, wait for signed doc 12/3 got sample ,function check (文件&寄樣) | 2020-12-03 | 2021-01-22 | MMN-WWAN | (COO) CMIIT ID: 2021CP0465 | V (2021/5/6) |  |  | 5 |  |  | 3675
|  |  | 2020-12-10 | 18 | 2020-12-28 | 01/06,13 in test 12/29 in test (受理&排測) | 2020-12-23 | 2021-01-22
|  |  | 2020-12-28 | 21 | 2021-01-18 | (測試) | 2020-12-29 | 2021-01-22
|  |  | 2021-01-18 | 35 | 2021-02-22 | 01/20 got Id, wait for cert (審理&取證) | 2021-01-20 | 2021-01-22
| NAL (CIT) | T77W968+AX201 | 2020-11-30 | 130 | 2021-04-19 | 4/21 waiting for scan file 04/07, 14 under authority review 03/31 got the DELL signed letter to issued report, schedule maybe postpone 03/23 test finished, report typing (require DELL signed letter to issued report ) 03/10 SSD sent out, local agent will update OS after SSD received 03/03 waiting for solution ,schedule maybe postpone 02/17,24 in test 02/03 wait for solve issue 01/13,20,27 in test 12/29, 1/6 in test ,under debug fail issue 12/23 wait for test 12/16 wait for doc 12/09 sample in transit 12/02 prepare for sample delivery China Holiday:2/11~2/17 Booking Intel TW lab for WAPI pre-test with Intel FAE Frank.(refer to Augusta MLK's mail) 8/31: Inquire Intel about booking lab for WAPI pre-test. 9/3: Intel suggest to wait till TGL PV is ready for test. Suggest to test it after ww42 timeframe. 9/10: Booking Intel TW lab for WAPI pre-test on 10/26 after 2 pm. contact Intel_Yang, Frank Fc | 2020-12-02 | 2021-04-23 | MMN-WWAN | Mii label | V (2021/5/6) |  |  | 17 | 2 |  | 27825
| NAL (CTY) | T77W968+AX201 | 2020-11-30 | 116 | 2021-03-26 | 5/25: Dell MKT- did not need PCP. |  |  |  | Mii label | V (Date) | [5 empty] | 0
| NAL (CDT) | T77W968+AX201 | 2020-11-30 | 130 | 2021-04-19 | 4/21 waiting for scan file 04/07, 14 under authority review 03/31 got the DELL signed letter to issued report, schedule maybe postpone 03/23 test finished, report typing (require DELL signed letter to issued report ) 03/10 SSD sent out, local agent will update OS after SSD received 03/03 waiting for solution ,schedule maybe postpone 02/17,24 in test 02/03 wait for solve issue 01/13,20,27 in test 12/29 in test ,under debug fail issue 12/23 wait for test 12/16 wait for doc 12/09 sample in transit 12/02 prepare for sample delivery China Holiday:2/11~2/17 Booking Intel TW lab for WAPI pre-test with Intel FAE Frank.(refer to Augusta MLK's mail) 8/31: Inquire Intel about booking lab for WAPI pre-test. 9/3: Intel suggest to wait till TGL PV is ready for test. Suggest to test it after ww42 timeframe. 9/10: Booking Intel TW lab for WAPI pre-test on 10/26 after 2 pm. contact Intel_Yang, Frank Fc | 2020-12-02 | 2021-04-23 |  | Mii label | V (2021/5/6) |  |  | 17 | 2 |  | 27825
Ecuador | ARCOTEL | AX201+RFID | 2021-02-23 | 56 | 2021-04-20 | 03/03,10, 17, 23 under review 02/24 got comment on photos, wait for additional pics 02/03,17 in process 01/26 application submitted pendint Module FCC grant for (DWRFID2002) spec,Wait for the local lab to confirm that the photos meet the requirements,TAC Letter | 2021-01-26 | 2021-03-29 |  |  | V (2021/5/6) | [5 empty] | 3150
Indonesia | SDPPI (Taiwan) |  | N/A | N/A | N/A | Indonesia not in tablet CSTL. |  |  | RMN | XXXXX/SDPPI/2020 5100 | V (Date) | [5 empty] | 0
| SDPPI (China) |  | N/A | N/A | N/A | Indonesia not in tablet CSTL. |  |  |  | XXXXX/SDPPI/2020 5100 | V (Date) | [5 empty] | 0
Jordan | TRC (RTN) | AX210+RFID | 2021-02-08 | 56 | 2021-04-05 | 03/11 wait for TRC feedback 03/03 got comment for model difference 02/03,17,24 in process 01/26 application submitted 12/10 transfer sample to local lab CE DOC | 2021-01-26 | 2021-03-18 | [8 empty] | 2205
Jordan | TRC (RTN) | AX210+RFID+T77W968 | 2021-02-08 | 66 | 2021-05-31 | 5/26 push cert. 5/19 under authority reivew, update ETA to 5/31 5/12 under authority reivew, update ETA to 5/21 5/5 under authority review, wait for dell check the marketing name-5/6 comfirm OK 4/28 under authority review, target date maybe postpone to 5/14) 4/23 DELL William reply comment 4/21 wait DELL to reply comment 4/07, 14 under authority review 03/31 got comment (require Declaration letter for WWAN SKU), schedule maybe postpone-3/31已補件 03/23 sample arrived, 先前因標籤問題我們有在提供一台樣品給當地.目前取證日更新為2021/04/15 03/11, 18 wait for TRC feedback 03/03 got comment for model difference 02/03,17,24 in process 01/26 application submitted 12/10 transfer sample to local lab CE DOC | 2021-01-26 | 2021-06-03 | RTN | [5 empty] | 1 |  | 2205
Korea | USIM report | T77W968 | 2020-11-30 | 35 | 2021-01-22 | 01/13 wait for report 12/23, 1/6 3G connection got problem, ETA will be delayed 12/16 wait for test 12/10 transfer sample to local lab | 2020-11-30 | 2021-01-21 | RTN |  |  |  |  | 1 |  |  | 788 | 收到報告結案
Malaysia | MCMC | All modules | 2021-02-01 | 42 | 2021-03-15 | 02/03,17,24, 3/3 in process 01/27 got signed doc, application will be submitted by tomorrow 01/20 wait for signed doc 12/29 SIRIM lab and office are all closed due to the outbreak of COVID-19 till 2021/1/4 不需要LOCAL TEST IPV6 wait for EMC report | 2021-01-28 | 2021-03-11 | RMN | (WW) MCMC Logo | V (2021/5/6) |  |  | 1 |  |  | 2573
Mexico | NOM-208/221 | All modules | 2021-01-08 | 56 | 2021-03-05 | 1/9-sample arrived Mexico airport 1/11-wait for DELL Mexico clearing samples 1/6 ship out sample assumption 1. sample no shipping/ clearance delay before 1/15 2. test completeion by 2/12 12/24 wait for Agent reply lead time local testing, max config, 2units no return | 2021-01-06 | 2021-02-24 | RMN |  | V (2021/5/6)
Mexico | IFETEL | All modules | 2021-03-05 | 84 | 2021-08-31 | 8/26, 9/2, 9, 16, 23, 30, 10/7, 14, 20, 27, 11/5, 12, 19, 26, 12/3, 10, 17 Need SAR report | 2021-02-24 |  | RMN | (ID on DELL sell website) IFT ID: | V (2021/5/6)
Morocco | ANRT | All modules | 2021-02-08 | 28 | 2021-03-08 | 02/03,17 in process 01/26 application submitted wait for CE DOC 最快3~3.5週取證，先抓4週 Label impact | 2021-01-26 | 2021-02-22 | RMN | (WW) N°D’AGRÉMENT MR00027198ANRT2021 (27/01/2021) | V (2021/5/6) | [5 empty] | 2310
Nigeria | NCC (Latitude 9510) | All modules | 2021-02-08 | 112 | 2021-05-31 | 02/03,17,24 in process 01/26 application submitted wait for CE DOC wait for EMC report | 2021-01-26 | 2021-03-04 | MMN | (UM) compliacne statement | V (2021/5/6) |  |  | 1 |  |  | 5775
Peru | MTC (Ministry of Transportation and Communications) | All modules | 2021-02-08 | 42 | 2021-03-22 | 02/03,17 in process 01/26 application submitted wait for TAC letter pending: CE DOC, spec wait for EMC report LT might be changed The outbreak of Covid- 19 are badly delaying the process Draft status of bulletin. Still waiting for Dell approval 9/16: 1. ADT reply L/T is 5~6wks and provide Checking list. 2. Still waiting for ADT deal contract price with Dell. | 2021-01-26 | 2021-02-23 | RMN |  | V (2021/5/6) | [5 empty] | 1890
Philippines | NTC | AX201 | 2021-02-08 | 42 | 2021-03-22 | 02/03,17 in process 01/26 application submitted pending CB cert, CB reprot, EMC report, CE DOC, sign document, SAR report | 2021-01-26 | 2021-02-19 | RMN+MMN |  | V (2021/5/6) | [5 empty] | 893
|  | AX201+RFID | 2021-02-08 | 42 | 2021-03-22 | 02/03,17 in process 01/26 application submitted pending CB cert, CB reprot, EMC report, CE DOC, sign document, SAR report | 2021-01-26 | 2021-02-19 | [8 empty] | 893
|  | AX201+T77W968 | 2021-02-08 | 42 | 2021-03-22 | 02/03,17 in process 01/26 application submitted pending CB cert, CB reprot, EMC report, CE DOC, sign document, SAR report | 2021-01-26 | 2021-02-19 |  | (IDV) ESD-GEC-2106566 | V (2021/5/6) | [5 empty] | 1134
|  | AX201+RFID+T77W968 | 2021-02-08 | 42 | 2021-03-22 | 02/03,17 in process 01/26 application submitted pending CB cert, CB reprot, EMC report, CE DOC, sign document, SAR report | 2021-01-26 | 2021-02-19 |  | (IDV) ESD-GEC-2106565 | [6 empty] | 1134
Saudi Arabia | CITC | AX201+RFID+T77W968 | 2021-03-11 | 42 | 2021-04-22 | 03/11 17, 23 in process 03/08 got CE DOC /SPEC 03/04 got CITC account and password. 3/03 wait for pended items ( CE DOC &SEPC 製造商需蓋章/CITC的帳密) 2/25 pending for lack documents | 2021-03-10 | 2021-03-29 |  | E-label | V (2021/5/6)
Thailand | SDoC | AX201 | 2021-02-01 | 35 | 2021-03-08 | 01/26 application submitted 1/20 got System report ,preparing submit 1/6 SAR report OK, wait for safety report wait for EMC report | 2021-01-26 | 2021-02-18 | RMN |  | V (2021/5/6) | [5 empty] | 1575
| Class B | T77W968+AX201 | 2021-02-01 | 42 | 2021-03-15 | 01/26 application submitted 1/20 got System report ,preparing submit wait for EMC report Label impact | 2021-01-26 | 2021-02-18 | RMN | (IDV) NBTC: B38050-21-0591 | V (2021/5/6) | [5 empty] | 2363
Taiwan | Conducted power report | T77W968 | 2020-11-30 | 35 | 2021-01-04 | 1/26 final reports 12/23,29, 1/6,13,20 waiting sample for 極限電壓測試, wait for safety BSMI report 12/10,16 under testing 12/04 arrange test 12/03 function check ok 12/02 got sample | 2020-11-30 | 2021-01-27 | RMN |  |  |  |  | 1 | 1 |  | 2023
| NCC add host |  | 2021-02-08 | 35 | 2021-03-15 | 02/04 in process 02/03 in process 01/27 got EMC &Safety report ,submit to RCB BSMI report Label impact | 2021-01-27 | 2021-02-05 |  | (IDV) CCAI20Y00120T9 CCAI18Z10130T2 | V (2021/5/6) V (2021/7/21) | [5 empty] | 1068
Zambia | ZICTA | All modules |  | 70 |  | 7/27: Bulletin-Zambia own by local distributor. 7/30: Compal ID have removed Zambia label from label plan. |  |  |  | (IDV) ZMB/ZICTA/TA/2020/2/40 | V (Date) | [5 empty] | 0
RFID Limited Module Approval | [13 empty] | proto | proto-keypad | NRE | Actual $
EU | 1. EN300330 2. EN301489 -1/-3 3. EN60950 4. EN62311 DoC | RFID | 2020-11-16 | 28 | 2020-12-14 | 12/08 preparing repors 12/07 finished test 11/26, 12/3 under testing -12/11給report 11/18-function check ok 11/16-got sample | 2020-11-16 | 2020-12-14 | RFID: DWRFID2002 | CE | V (2021/5/6) | V (2021/5/6) |  | 2 |  |  | 3465
Australia | AS/NZS 4268:2017 MPE | RFID | 2020-11-16 | 28 | 2020-12-14 | refer ce -12/11給report | 2020-11-16 | 2020-12-14 |  | RCM with R-NZ |  | V (2021/5/6) |  |  |  |  | 173
US | FCC Part 15C+New ID | RFID | 2020-11-16 | 42 | 2021-03-17 | 12/22 got FCC VOC 12/15 under submit 12/14 final reports 11/26, 12/3,10 under testing 11/18-function check ok 11/16-got sample | 2020-11-16 | 2021-02-22 |  | Contains FCC ID: E2K-DWRFID2002 | V (2021/5/6) | V (2021/5/6) |  | 2 | 1 |  | 3150
Canada | IC RSS 210+New ID | RFID | 2020-11-16 | 42 | 2020-12-28 | 12/22 got cert refer US Holidays :11/26~11/27, 12/25, 12/31~1/1 | 2020-11-16 | 2020-12-22 |  | Contains IC: 1514B-DWRFID2002 | V (2021/5/6) | V (2021/5/6) |  |  |  |  | 1748
Japan | Extremely low power report | RFID | 2020-11-16 | 35 | 2020-12-21 | 12/18 final repor 12/16 provide draft report 11/26, 12/3,10 under testing 11/18-function check ok | 2020-11-16 | 2020-12-18 |  |  |  | V (2021/5/6) |  |  |  |  | 1050
Korea | Radio-Telecom test for RFID | RFID | 2020-11-16 | 42 | 2020-12-28 | 12/23 wait for EMC to issue final report 12/15 provide draft reports 12/02 wait for test 11/26-sample in local lab,waiting for testing 11/18-function check ok ,transfer sample to local lab | 2020-11-16 | 2021-02-22 |  |  |  | V (2021/5/6) |  |  |  |  | 5460
Taiwan | NCC LP0002+Cert (9*adatper) | RFID | 2020-11-16 | 42 | 2020-12-28 | 12/22 got 1 st comment 12/18 udner submit 12/18 got NCC copy letter and under submit NCC 12/15 informed final report 12/10 finshed test 11/26, 12/3-under testing 11/18-function check ok 12/18前要送件才能取今年證書 | 2020-11-16 | 2020-12-25 |  | CCAI20Y20040T0 | V (2021/5/6) | V (2021/5/6) |  | each adapter*1 |  |  | 4725
RFID WW Approval | [13 empty] | proto | proto-keypad | NRE | Actual $
Antiqua And Barbuda | MBT | RFID | 2020-12-14 | 42 | 2021-01-25 | 12/23,29, 1/6 in process 12/17 application submitted LT might be changed The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2021-01-09 | RFID: DWRFID2002 |  | V (2021/5/6) | [5 empty] | 1680
Armenia | ANAB | RFID | 2020-12-14 | 28 | 2021-01-11 | 12/23,29, 1/6 in process 12/17 application submitted | 2020-12-17 | 2021-01-07 |  | ANAB compliance Mark (Voluntary) | V (2021/5/6) | [5 empty] | 3150
Aruba | DTZ | RFID | 2020-12-14 | 78 | 2021-03-02 | 02/03 in slow process 01/27 per phone call last Friday with DTZ, parts of the technical reviewers and accountants are currently in quarantine, so the certification process has been delayed. We requested them to proceed our application with priority once they are back to the office, however, the ETA is still gonna be postponed til 3/2. 1/26 parts of the technical reviewers and accountants are currently in quarantine, so the certification process has been delayed, however, the ETA is still gonna be postponed til 3/2. Thanks for your understanding 12/23,29, 1/6,13,20 in process 12/17 application submitted | 2020-12-17 | 2021-02-05 |  |  | V (2021/5/6) | [5 empty] | 1785
Bahamas | URCA | RFID | 2021-02-23 | 56 | 2021-04-20 | Wait FCC grant 3/25 | 2021-02-23 | 2021-01-09 |  |  | V (2021/5/6) | [5 empty] | 1050
Bahrain | iGA | RFID | 2020-12-14 | 42 | 2021-01-25 | 12/23,29, 1/6,13 in process 12/17 application submitted | 2020-12-17 | 2021-01-18 |  |  | V (2021/5/6) | [5 empty] | 2100
Barbados | TU | RFID | 2020-12-14 | 28 | 2021-01-11 | 12/23,29 in process 12/17 application submitted | 2020-12-17 | 2021-01-05 |  |  | V (2021/5/6) | [5 empty] | 1575
Belize | PUC | RFID | 2020-12-14 | 56 | 2021-02-08 | 12/21 got cert | 2020-12-17 | 2020-12-21 |  |  | V (2021/5/6) | [5 empty] | 1943
Bolivia | ATT | RFID | 2020-12-14 | 98 | 2021-03-22 | 12/23,29, 1/6,13,20,27,2/3,17,24 in process 12/17 application submitted LT might be changed The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2021-03-02 |  |  | V (2021/5/6) | [5 empty] | 1890
Botswana | BOCRA | RFID | 2020-12-14 | 49 | 2021-02-01 | 12/23 in process 12/17 application submitted | 2020-12-17 | 2020-12-28 |  | BOCRA REGISTERED No : BOCRA/TA/2020/5875 | V (2021/5/6) | [5 empty] | 2363
Cambodia | MPTC (Taiwan+China) | RFID | 2020-12-14 | 73 | 2021-02-25 | 03/11 TRA approved the final template, checking application status: 1 COO each certification required, submitted 2nd COO as Taiwan, 1st as China. 02/24, 3/3 applicaiton under review, but still waiting TRA to approve the final certificate template. 1/27,2/3,17 The application has been filed, but ETA cannot be defined as Cambodia TRC has esumed approval effort and approved the final certificate template. 1/13 lead time from 2/25 change to TBD, since authority change procedure of certification 12/29,1/06,1/13,1/20 wait for submission notification from authority 12/29, 1/6,13 wait for submission notification from authority 12/23 Lead time will become longer due to new change of internal procedure and new certificate template in TRC. Projects will be delayed due to the re-design of the certificate template by the regulator. For the time-being we are not able to provide a specific lead time for the project. We were told that we will get the official letter informing us of the delay. We were advised to not submit the application now and wait until we get the official letter from the regulator. | 2020-12-17 | 2021-03-18 |  |  | V (2021/5/6) | [5 empty] | 2940
Costa Rica | SUTEL | RFID | 2020-12-14 | 56 | 2021-02-08 | 1/6 in process 12/19-1/03 holiday, l/t change to 8wks 12/17 application submitted | 2020-12-17 | 2021-01-09 |  |  | V (2021/5/6) | [5 empty] | 1575
Cote D'ivoire | ARTCI | RFID | 2020-12-14 | 84 | 2021-03-08 | 12/23,29, 1/6,13,20,27 in process 12/17 application submitted | 2020-12-17 | 2021-02-03 |  |  | V (2021/5/6) |  |  | 1 |  |  | 2625
Dominica | NTRC | RFID | 2020-12-14 | 84 | 2021-03-08 | 12/23,29, 1/6,13 in process 12/17 application submitted | 2020-12-17 | 2021-01-21 |  |  | V (2021/5/6) | [5 empty] | 2205
Dominican Republic | INDOTEL | RFID | 2021-02-23 | 70 | 2021-05-04 | 01/20,27,2/3,17,24, 3/3 in process 01/13 application in process using CE plus WW cert Wait FCC grant, can try to submit application using CE if there is any WW cert | 2021-02-23 | 2021-03-11 |  |  | V (2021/5/6) |  |  | 1 |  |  | 2205
Egypt | NTRA | RFID | 2020-12-14 | 56 | 2021-02-08 | 12/23,29, 1/6 in process 12/17 application submitted | 2020-12-17 | 2021-01-11 |  |  | V (2021/5/6) | [5 empty] | 1260
Eswatini (舊名 Swaziland) | SCCOM | RFID | 2020-12-14 | 77 | 2021-03-01 | 01/27 there has been a high surge of COVID cases there, something that has prompted the regulator to work from home for the next 3 weeks and this will have an impact on deadlines. We expect a delay for three weeks. The new target date is March 1st. 1/26 Eswatini 因為疫情升溫，官方已經被通知接下來兩週在家上班，因此，發證時間會受影響。預計將會延遲 3 週發證，因此，預估 3/1才能取證。 01/13,20 in process 12/18-1/11 holiday 12/17 application submitted | 2020-12-17 | 2021-02-04 |  |  | V (2021/5/6) | [5 empty] | 2415
Fiji | TAF | RFID | 2020-12-14 | 46 | 2021-01-29 | 12/23,29, 1/6 in process 12/17 application submitted | 2020-12-17 | 2021-01-14 |  |  | V (2021/5/6) | [5 empty] | 1050
Ghana | NCA | RFID | 2020-12-14 | 49 | 2021-02-01 | 12/23,29 in process 12/17 application submitted | 2020-12-17 | 2021-01-07 |  | NCA APPROVED: SR0-1M-7E4-280 | V (2021/5/6) | [5 empty] | 2415
Grenada | NTRC | RFID | 2020-12-14 | 70 | 2021-02-22 | 12/23,29, 1/6,13 in process 12/17 application submitted | 2020-12-17 | 2021-01-21 |  |  | V (2021/5/6) | [5 empty] | 1260
Guyana | PUC | RFID | 2021-02-23 | 168 | 2021-08-10 | 03/03,10, 17, 23 in process 02/23 application submitted 1/13 target date change from 9/14 to TBD 12/23 Process on hold due to new regulation/process will be announced LT can not be defined Process on hold due to new regulation/process will be announced Wait FCC grant 3/25 | 2021-02-23 | 2021-04-12 |  |  | V (2021/5/6) | [5 empty] | 840
Haiti | CONATEL | RFID | 2020-12-14 | 140 | 2021-05-03 | 12/23,29, 1/6,13,20,27,2/3,17,24 in process 12/17 application submitted | 2020-12-17 | 2021-03-02 |  |  | V (2021/5/6) |  |  | 1 |  |  | 3360
India | DoT (China) | RFID | 2020-12-14 | 84 | TBD | 2/17,24, 3/3,10,18, 23, 31, 4/7, 14, 21, 28, 5/5, 12, 19, 26, 6/2, 9, 16 Applications with China Manufacturing are on hold by WPC Department and we can't mention you any date right now for the rest applications because we didn't get any update from WPC for the pending applications. 2/8 印度當局無限期HOLD 產地為大陸的申請推測是政治因素, 因近期中印雙方情勢緊張.還請先high light (原3/8) Applications with China Manufacturing are on hold by WPC Department and we can't mention you any date right now for the rest applications because we didn't get any update from WPC for the pending applications. 01/27,2/3 in slow process 1/21 in process ,Because COVID-19 and some changes on portal (technical issues) all submitted applications are going to take 4-5 more weeks to get the approval. 12/23,29, 1/6,13 in process 12/17 application submitted LT might be changed The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2021-06-23 |  |  | V (2021/6/23) | [5 empty] | 2310
| DoT (Taiwan) | RFID | 2020-12-14 | 84 | 2021-03-08 | 01/27,2/3 in slow process 1/21 in process ,Because COVID-19 and some changes on portal (technical issues) all submitted applications are going to take 4-5 more weeks to get the approval. 12/23,29, 1/6,13 in process 12/17 application submitted LT might be changed The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2021-02-08 |  |  | V (2021/5/6) | [5 empty] | 2310
Israel | MoC | RFID | 2020-12-14 | 119 | 2021-04-12 | 12/11~12/27 Holiday application will be sumitted by 12/27 | 2020-12-17 | 2021-01-04 |  | 55-06739 | V (2021/5/6) | [5 empty] | 2625
Jamaica | SMA | RFID | 2020-12-14 | 49 | 2021-02-01 | 12/23,29 in process 12/17 application submitted | 2020-12-17 | 2021-01-04 |  |  | V (2021/5/6) | [5 empty] | 2310
Kiribati | CCK | RFID | 2020-12-14 | 70 | 2021-02-22 | Handled by DELL importer |  |  |  |  | V (Date) | [5 empty] | 0
Kuwait | CITRA | RFID | 2020-12-14 | 71 | 2021-02-23 | 12/23,29, 1/6,13,20 in process 12/17 application submitted | 2020-12-17 | 2021-01-26 |  |  | V (2021/5/6) | [5 empty] | 2520
Lao, People'S Democratic Republic | MPT | RFID | 2020-12-14 | 42 | 2021-01-25 | 12/23 in process 12/17 application submitted | 2020-12-17 | 2020-12-29 |  |  | V (2021/5/6) | [5 empty] | 2363
Lebanon | TRA/MoT | RFID | 2020-12-14 | 284 | 2021-09-24 | 02/17,24,3/3,10, 4/7, 14, 21, 28, 5/5,12, 19, 26, 6/2, 9, 16, 23, 30, 7/7, 14, 21, 28, 8/4, 11, 18 resume to work, in slow process Lockdown from 2021/1/08~2021/02/012021/02/05, from 9/24 change to TBD 12/23,29, 1/6 in process 12/23 Application was submitted to MoT. Because of COVID-19, everything is super slow in Lebanon. In addition, they were affected by the bomb blast. The office was affected and they rebuilding their office for a long time 12/10 lead time 271 days TBD: explosion at port Need to update LT to 32wks The outbreak of Covid- 19 are badly delaying the process. In addition, they were affected by the bomb blast. The office was affected and they rebuilding their office for a long time. | 2020-12-17 | 2021-08-24 |  |  | V (2021/8/24) | [5 empty] | 2310
Malawi | MACRA | RFID | 2020-12-14 | 79 | 2021-03-03 | 02/17 The application are in process but due to Covid they are working from home and this has delayed to meet the deadline on time . The new ETA is likely to be postponed til 3/3.(original 2/12) 2/8 The application are in process but due to Covid they are working from home and this has delayed to meet the deadline on time . The new ETA is likely to be postponed til 3/3. Thanks for your understanding. (original 2/8) 12/23,29, 1/6,13,20,27,2/3 in process 12/17 application submitted | 2020-12-17 | 2021-02-19 |  |  | V (2021/5/6) | [5 empty] | 2310
Malaysia | MCMC | RFID | 2020-12-14 | 79 | 2021-03-03 | 12/23,29, 1/6,13 in process 12/17 application submitted | 2020-12-17 | 2021-01-21 |  |  | V (2021/5/6) |  |  | 1 |  |  | 2310
Mexico | IFETEL | RFID | 2020-12-14 | 116 | 2021-04-09 | 01/27,2/3,17,24,3/3,10 in slow process 01/21 outbreak of COVID-19, office closed (original 4/9) 01/13 in process 12/19~ 01/07 holiday, IFETEL reviewer start to work on 2021/1/11, the cases will increase significantly, so it will take a little more time for the authority review 12/23 in process 12/17 application submitted Need to update LT to 14wks The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2021-03-12 |  | IFT ID: RCPDEDW21-0495 | V (2021/5/6) | [5 empty] | 3990
Moldova | DoC (CIT+PCP+CDT) | RFID | 2020-12-14 | 112 | 2021-04-05 | 02/17,24,3/3,10 in process 02/03 waiting signed documents 12/23,29, 1/6,13,20,27 in process 12/22 submitted to Moldova authority 12/17 application submitted | 2020-12-17 | 2021-03-25 |  | SM Mark + cert. body no. (024) | V (2021/5/6) |  |  | 1 |  |  | 3150
Mongolia | CRC (Taiwan+China) | RFID | 2020-12-14 | 56 | 2021-02-08 | 12/23,29, 1/6,13 in process 12/21 application submitted | 2020-12-17 | 2021-01-18 |  |  | V (2021/5/6) | [5 empty] | 1260
Nicaragua | TELCOR | RFID | 2020-12-14 | 113 | 2021-04-06 | 01/27,2/3,17,24,3/3,10 in process 1/20 we received the following message from agent, informing that the delay is ongoing due to the change of certificate format. 12/23,29, 1/6,13,20 in process 12/17 application submitted | 2020-12-17 | 2021-03-25 |  |  | V (2021/5/6) | [5 empty] | 1890
Oman | TRA + authorization | RFID | 2020-12-14 | 42 | 2021-01-25 | 12/23 in process 12/17 application submitted | 2020-12-17 | 2020-12-28 |  | OMAN - TRA D172338 TRA/TA-R/10704/20 | V (2021/5/6) | [5 empty] | 2100
Panama | ASEP | RFID | 2020-12-14 | 70 | 2021-02-22 | 1/6,13 in process 12/18-1/04 holiday 12/17 application submitted | 2020-12-17 | 2021-01-18 |  |  | V (2021/5/6) | [5 empty] | 1890
Papua New Guinea | NICTA | RFID | 2020-12-14 | 49 | 2021-02-01 | 12/23,29, 1/6,13 in process 12/17 application submitted LT can not be defined The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2021-01-21 |  |  | V (2021/5/6) | [5 empty] | 1575
Paraguay | CONATEL | RFID | 2020-12-14 | 113 | 2021-04-06 | 12/23,29, 1/6,13 in process 12/17 application submitted | 2020-12-17 | 2021-01-21 |  | (on USH) NR: 2020-12-I-0947 | V (2021/5/6) | [5 empty] | 2888
Saint Kitts And Nevis | NTRC | RFID | 2020-12-14 | 84 | 2021-03-08 | 02/17 got draft, wait for final cert 12/23,29, 1/6,13,20,27,2/3 in process 12/17 application submitted | 2020-12-17 | 2021-02-19 |  |  | V (2021/5/6) | [5 empty] | 945
Saint Lucia | NTRC | RFID | 2020-12-14 | 126 | 2021-04-19 | 02/17,24,3/3,10, 23 in process, they have been having delays because of the situation with the pandemic that is critical at the moment. Kindly note it will possibly delay the process 12/23,29, 1/6,13,20,27,2/3 in process 12/17 application submitted | 2020-12-17 | 2021-04-01 |  |  | V (2021/5/6) | [5 empty] | 1575
Saudi Arabia | CITC | RFID | 2020-12-14 | 42 | 2021-01-25 | 9/3: Compal RF reg. Wayne. Lu inform Dell Jack Saudi Arabia is no longer accept WLAN/RFID module certification. *under confirming with BV-ADT, BV insist that WLAN/RFID is no longer accept module/system approval Dell RCE Jack: 1. no, not system approval 2. Tablets with WWAN modules need to display the CITC approval number for the WWAN module (Type approval number) as an electronic label ( E-Label). 9/15: Action Plan Deliverables *Use WWAN Module CITC cert number for sustaining platforms *Use Host CITC cert number for NPI platforms. *E-Label require to put label request form/document request form. Cost Inquire BV about cost, BV doesn't have Dell contract price. Waiting for BV Kevin & Dell to deal price. |  |  |  | TA xxxx-y CITC E-Label | V (Date) | [5 empty] | 0
Senegal | ARTP | RFID | 2020-12-14 | 70 | 2021-02-22 | 12/23,29, 1/6,13,20,27,2/3 in process 12/17 application submitted | 2020-12-17 | 2021-02-18 |  |  | V (2021/5/6) | [5 empty] | 2730
Serbia | KVALITET | RFID | 2020-12-14 | 46 | 2021-01-29 | 12/23,29, 1/6,13 in process12/17 application submitted | 2020-12-17 | 2021-01-18 |  | Ratel mark (И005 21) | V (2021/5/6) | [5 empty] | 1890
Singapore | iMDA | RFID | 2020-12-14 | 14 | 2020-12-28 | 12/23 in process 12/17 application submitted | 2020-12-17 | 2020-12-29 |  | This device contains DWRFID2002 module. Complies with iMDA standards DA104808 | V (2021/5/6) | [5 empty] | 630
Solomon Islands | TCSI | RFID | 2020-12-14 | 84 | 2021-03-08 | approval on hold, The authority is waiting for the Minister to mandate if the new acting Commissioner has the authority to approve applications and sign approvals. And until this happens, type approvals are on hold again. TBD: wait local gov. revise standard LT can not be defined In February 2020, authority suspened all of type approvals including our application which is submitted in December 2019 because of ITU issue In June, New Commissioner starts type approval work, but no certificate is released so far. | 2020-12-17 | 2021-02-25 |  |  | V (2021/5/6) | [5 empty] | 1365
South Africa | ICASA | RFID | 2020-12-14 | 133 | 2021-04-26 | 1/6,13,20,27,2/3,17,24,3/3 in process 12/15~1/5 Holiday 12/17 application submitted | 2020-12-17 | 2021-03-09 |  | (IDV) ICASA label TA-2020/8117 | V (2021/5/6) | [5 empty] | 2625
Suriname | TAS | RFID | 2020-12-14 | 56 | 2021-02-08 | 1/6,13,20 in process 12/15~1/5 Holiday 12/23,29 in process 12/17 application submitted LT can not be defined, might be 10-12wks The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2021-01-27 |  |  | V (2021/5/6) | [5 empty] | 1523
Tanzania | TCRA | RFID | 2020-12-14 | 49 | 2021-02-01 | 1/6,13,20 in process 12/15~1/5 Holiday 12/23,29 in process 12/17 application submitted | 2020-12-17 | 2021-01-26 |  |  | V (2021/5/6) | [5 empty] | 2321
Tunisia | CERT | RFID | 2020-12-14 | 60 | 2021-02-12 | Lockdown form 2021/1/14~2021/1/17 1/6 in process 12/15~1/5 Holiday 12/23,29 in process 12/17 application submitted | 2020-12-17 | 2021-01-18 |  |  | V (2021/5/6) |  |  | 1 |  |  | 4725
UAE | TRA | RFID | 2020-12-14 | 42 | 2021-01-25 | 12/15~1/5 Holiday 12/17 application submitted | 2020-12-17 | 2020-12-28 |  | TRA REGISTERED No: ER92929/20 DEALER No: 0032863/10 | V (2021/5/6) |  |  | 2 |  |  | 2940
Uruguay | URSEC | RFID | 2020-12-14 | 39 | 2021-01-22 | 1/6 in process 12/29 The outbreak of Covid- 19 are badly delaying the process, ETA will be delayed to 1/22 12/15~1/5 Holiday 12/17 application submitted | 2020-12-17 | 2021-01-09 |  |  | V (2021/5/6) | [5 empty] | 1995
Venezuela | CONATEL | RFID | 2020-12-14 | 35 | 2021-01-18 | 12/23 cert done LT can not be defined, might be 6-10wks The outbreak of Covid- 19 are badly delaying the process | 2020-12-17 | 2020-12-24 |  |  | V (2021/5/6) | [5 empty] | 1995
Vietnam | report only RF-EMC (QCVN96) RF (QCVN55) | RFID | 2020-12-14 | 42 | 2021-01-25 | 12/23,29 wait for report | 2020-12-17 | 2021-01-05 |  |  | V (2021/5/6) | [5 empty] | 1365
Zimbabwe | POTRAZ | RFID | 2020-12-14 | 113 | 2021-04-06 | 02/17,24, 3/3,10 in procss 02/03 checking if authority resume to work 1/13 lockdown from 2021/1/03-2021/1/31, target date change from 3/8 to 4/6 12/23,29, 1/6 in process 12/17 application submitted | 2020-12-17 | 2021-03-19 |  |  | V (2021/4/20) | [5 empty] | 2625
503526
Date | Notes. | [6 empty] | AX201D2W | T77W968 | DWRFID2002
2020-06-01 | Receive final BA letter from PM Ted. | [6 empty] | OMAN - TRA | OMAN - TRA | OMAN-TRA
2020-06-02 | Update RF schedule on the Carnoustie 13 schedule_X07: pull in RFD 1 week from 3/12’21 to 3/5’21. | [6 empty] | D080001 | D100428 | D172338
2020-06-18 | Increase proto demand due to additional WWAN 2nd source to PM. | [6 empty] | TRA/TA-R/6647/18 | TRA/TA-R/5917/18 | TRA/TA-R/10704/20
2020-06-20 | Use P Sensor
2020-07-01 | DVT1 Proto checking 1. USH/B (CV3 chip): RD Ivan- Security function基本上就是綁著Broadcom的CV3 chip也就是USH小板， 所以Non-Security Sku沒有USH是正常的。 USH小板跟NFC有關係，如果妳有要做相關認證的話建議還是要book有USH的sku喔， 因為"機殼外觀也有分薄的跟厚的，厚的才有空間裝得下USH小板。 2. On board WLAN Antenna: N/A -->Waiting for Compal PJE response.
2020-07-09 | AIO Label: RF Label will have updated version that add Argentina/Mexico/Morocco.--> Need discuss and aligne with Dell Marketing team and CT.
2020-07-10 | PJE Geen inform power cord will deliver to TPE that need to deliver from TPE to LKE Domo --> 7/14 received and send to LKE Domo.
2020-07-14 | Inform ID Aven to add MCMC Logo to country label of label location.
2020-07-14 | 1. Proposal to revise the MMN to "Latitude 7320 Detachable"-->Waiting for MKT team confirm it. 2. Tablet will require to conduct Limb SAR--> Check with Lab how to conduct France Limb SAR
2020-07-15 | WWAN module certification of T77W968: FCC ID: MCLT77W968-D10 Saudi Arabia ID: TA 2018-937 (E-Label New request)
2020-07-21 | CR 8535 has been approved by CT today. Carnoustie marketing name is now officially changed to “Latitude 7320 Detachable” which will be applicable to all items that require marketing name information.
2020-07-24 | Bulletin Peru: Provide the documents to Dell importer befor 6 weeks of RFD-->Change to ODM own. Need PCR to get cost.
2020-07-30 | 1. A31 projects have CHV transition plan as below. A31 projects have CHV transition plan as below. 2. Ask PJE booking additional adapter for Brazil (36 per adapter)
2020-08-06 | Provide the shipping plan to Domo.
2020-08-19 | Inform PM Booking DVT1.1 Non-Security Sku: 3units / Security Sku: 3units *DVT1.0+DVT1.2 Total units: Non-Security Sku: 62units / Security Sku: 43units
2020-08-24 | LRF & DRF by COB 8/27-->8/26 updated
2020-08-26 | Due to 65W adapter (Huntkey) P-RTS, update certification that add adapter after RTS will have cost impact as below. Inform PM will have adder NRE for this. -->PM reply that not sure if we can get the certification fee. 1. Taiwan (LP0002): per adapter USD$525 (w/tax) 2. Brazil (ANATEL): per adapter USD$4,725 ((USD$3,000 test fee+ USD$1,500 review fee)*1.05 w/tax)
2020-08-27 | Pen design changed from Wacom AES 2.0 to AES 1.0 that inform PM SWAP to AES1.0 Pen. DVT1.1 AES1.0 ETA: 2020/10/27
2020-09-03 | Initial LRF completed with Safety & Green.
2020-09-09 | Dell Lin, Nami: Carnoustie label vendor is confirmed, CCL.
2020-09-14 | Inform PJE Green to add Miya. Lan to team member list.
2020-09-15 | Provide RF regulatory comments for label drawing (CCL) to LKE RCE Stella.
2020-10-13 | 不開沙烏地阿拉伯，不能進行.WWAN模組證號放e-Label, others 不放也不做
2020-10-15 | Domo通知，機台目前有issue, For WLAN+WWAN+RFID (secutity sku) 會掉卡，RFID/ WWAN 會互搶資源，WWAN都搶輸。 目前討論 + hub, 結合switch 可改善。但不確認目前什麼時候可完成。有可能會延誤機台。會再跟Lab con-call
2020-10-16 | 天線未ready, 需要晚一週，但我沒有答應
2020-11-06 | SAR fail to 16~17, 預計11/9 再確認狀況
2020-11-11 | 預計11/19 先寄出Intel 樣品，會再麻煩Wan 收集文件
2020-11-19 | no updated
2020-11-25 | Reschedule, since EMC report will delay, lead to SDOC complete lately, 11/16 change to 12/14, and will cause PRTS and label impact
2020-12-04 | Carnoustie PRTS的國家(亞塞拜然、約旦)需要DELL支援CE DOC提前簽核，並於2/2前送審，才不會導致PRTS
2020-12-10 | Lebanon lead time chage to 2021/9/11
2020-12-17 | RFID CE DOC provide to LAB
2020-12-21 | Belize (RFID) done
2020-12-24 | Venezuela(RFID) done
2020-12-24 | Mexico 更新日期為2020/4/9 估計IFETEL官方放假回來上班後, 案件量會大增, 所以會需要多一點時間讓官方審件 Holiday: 12/19-1/7, IFETEL reviewer預計1/11才會恢復上班 Cambodia TRC 最近在更改內容審件流程及審件的內部文件，連證書版本都要更新，因此，最近的案件都已受到影響而 delay。 Costa Rica:日期為2020/2/8(因12/19-1/03 holiday)
2020-12-25 | Taiwan (RFID) Done
2020-12-28 | Oman, UAE, Botswana (RFID) done
2020-12-29 | Singapore (RFID) Done Lao (RFID) Done Belarus Done
2020-12-30 | Uruguay: The outbreak of Covid- 19 are badly delaying the process, ETA will be delayed to 1/22
2020-12-31 | WLAN AX201D2W ant filing submitted
2021-01-04 | Israel (RFID) Done Jamaica (RFID) done
2021-01-05 | Barbados (RFID) done Vietnam (RFID) done
2021-01-07 | Armenia (RFID) done Ghana (RFID) done
2021-01-09 | Antigua & Barbuda (RFID) done Bahamas (RFID) done Costa Rica (RFID) done Uruguay (RFID) done
2021-01-11 | Egypt (RFID) deone
2021-01-14 | Chile cert done Fiji (RFID) done
2021-01-14 | Cambodia: TBD, authority change procedure of certification, LT can not be defined Guyana: new regulation/process will be announced, LT can not be defined Lebanon: COVID-19 outbreak, Lockdown from 2021/1/08~2021/02/01 Zimbabwe: COVID-19 outbreak, lockdown from 2021/1/03-2021/1/31
2021-01-18 | Bahrain (RFID) done Mongolia (RFID) done Panama (RFID) done Serbia (RFID) done Tunisia (RFID) done
2021-01-21 | Korea SAR report done Korea USIM report done Malaysia (RFID) cert done Papua New Guinea (RFID) cert done Paraguay (RFID) cert done Dominica (RFID) cert done Grenada (RFID) cert done
2021-01-21 | 因印度疫情嚴峻及最近他們系統出現問題,所以目前的拿證時間會在延後4-5周, from local: We just had a words with WPC Department and they said that due to some changes on portal (technical issues) all submitted applications are going to take 4-5 more weeks to get the approval.
2021-01-22 | China SRRC WWAN SKU cert done
2021-01-26 | 阿魯巴 Aruba I’m writing this email to inform you that per phone call last Friday with DTZ, parts of the technical reviewers and accountants are currently in quarantine, so the certification process has been delayed. We requested them to proceed our application with priority once they are back to the office, however, the ETA is still gonna be postponed til 3/2. Thanks for your understanding Eswatini: Eswatini預估取證日由 2/08 延至 3/1。 Eswatini 因為疫情升溫，官方已經被通知接下來兩週在家上班，因此，發證時間會受影響。 預計將會延遲 3 週發證，因此，預估 3/1才能取證。 請見 agent 回覆如下： Regarding Eswatini (Swaziland), there has been a high surge of COVID cases there, something that has prompted the regulator to work from home for the next 3 weeks and this will have an impact on deadlines. We expect a delay for three weeks. The new target date is March 1st. I follow closely this project, I will keep you updated
2021-01-26 | Kuwait (RFID) done Tanzania (RFID) done
2021-01-27 | Suriname (RFID) done
2021-01-29 | Japan report and cert. done
2021-02-02 | FCC VOC done
2021-02-03 | China SRRC (WLAN) done Canada Cert. done Cote D'ivoire (RFID) done
2021-02-04 | Eswatini (舊名 Swaziland) (RFID) done
2021-02-05 | Aruba (RFID) done Taiwan NCC WWAN add host cert done
2021-02-08 | Malawi: The application are in process but due to Covid they are working from home and this has delayed to meet the deadline on time . The new ETA is likely to be postponed til 3/3. Thanks for your understanding.
2021-02-08 | Azerbaijan done India (Taiwan) done, India (China):印度當局無限期HOLD 產地為大陸的申請推測是政治因素, 因近期中印雙方情勢緊張.還請先high light Applications with China Manufacturing are on hold by WPC Department and we can't mention you any date right now for the rest applications because we didn't get any update from WPC for the pending applications.
2021-02-18 | Thailand done Senegal (RFID) done
2021-02-19 | Malawi (RFID) done Saint Kitts and Nevis (RFID) done Philippines done
2021-02-22 | Morocco done Korea (RFID) done
2021-02-22 | FCC Grant done FCC (RFID) Cert done
2021-02-23 | Peru Done
2021-02-24 | Mexico NOM done (System)
2021-02-25 | Solomon Islands (RFID) done
2021-02-25 | add Saudi Arabia system certification
2021-03-02 | Bolivia (RFID) done Haiti (RFID) done
2021-03-04 | Nigeria done
2021-03-09 | Argentina done South Africa (RFID) done
2021-03-11 | Dominican Republic (RFID) done Malaysia done
2021-03-12 | Mexico (RFID) done
2021-03-18 | Jordan RFID+WLAN done Cambodia Taiwan (RFID) done
2021-03-19 | Zimbabwe (RFID) Done
2021-03-24 | Nicaragua (RFID) Done Moldova (RFID) Done
2021-03-25 | PJM Connie: no blackchin 60W adaptor to Brazil.
2021-03-29 | Saudi Arabia (System) Done
2021-04-01 | Saint Lucia (RFID) Done
2021-04-12 | Guyana (RFID) Done Chinal NAL will be postpone to 4/19 Jordan will be postpone to 4/30
2021-04-23 | Chinal NAL Cert. done
2021-04-28 | Jordan target date maybe postpone to 5/14
2021-05-06 | Jordan: comfirm the marketing name of certificate Brazil: ETA will be updated to 5/17.
2021-05-11 | Brazil: cert. done by 5/11 Jordan: update ETA 5/21
2021-05-10 | Jordan: update ETA 5/31 (因本周剛結束齋戒月開始審閱,故延後取證日)
2021-05-26 | Mexico (system): update ETA to 7/16
2021-06-03 | Jordan: cert. done
2021-06-15 | Mexico (system): update ETA to 8/31
2021-06-23 | India (RFID) Done
2021-07-20 | Taiwan: update NCC ID to CCAI18Z10130T2 (for change Applicant to Fibocomm)
2021-08-24 | Lebanon (RFID): cert. done Mexico (System): update IFT certification status
Formulas:
Start Date = [Target Date, row above]
Target Date = [Start Date]+[L/T]
Target Date = SUM([Start Date]:[L/T])
Note on J2: Liu. Wan (TPE): 舊規IEC 60950-1 新規:IEC 62368-1
Note on J4: Su. CindyHC (TPE): For WWAN NCC add host CNS 13438 EMC CNS 14336 Safety
Note on K6: Liu. Raura (TPE): RD pull in 6wks to 3wks for WWAN 2 source
Note on G17: Liu. Wan (TPE): 12/18 韓國當地收到WWAN天線報告後確認WWAN+WIFI及WIFI only 內的WIFI 天線位置都相同,因此follow Korea新規標準 只需出一本WWAN+WIFI SAR report ,
Note on S19: Liu. Wan (TPE): WWAN test (WLAN-copy CE)
Note on D27: Liu. Wan (TPE): 預計11/30送件(WLAN DVT1.0+10day)
Note on B67: Huang. Elaine (TPE): Approval is exempted if Field Strength is < 500uV/m @ 3m
Note on B69: Liu. Wan (TPE): 11/18- 9顆Adapters
Note on E73: Liu. Wan (TPE): 1/26 reviewers被隔離
Note on E80: Liu. Wan (TPE): 12/23 BV:Cambodia TRC 最近在更改內容審件流程及審件的內部文件，連證書版本都要更新，因此，最近的案件都已受到影響而 delay。 官方還在討論證書樣式的修改方向，這需要花一段時間才會定案。我們被官方要求先不要送件，等官方通知可以送件時，才能投件。 還不知道何時才能投件，因此，我先把預估取證日改成 2021/2/25。
Note on F80: Liu. Wan (TPE): Lead time will become longer due to new change of internal procedure and new certificate template in TRC. Projects will be delayed due to the re-design of the certificate template by the regulator. For the time-being we are not able to provide a specific lead time for the project. We were told that we will get the official letter informing us of the delay. We were advised to not submit the application now and wait until we get the official letter from the regulator.
Note on E81: Liu. Wan (TPE): 12/23 BV: 12/19-1/03 holiday
Note on F90: Liu. Wan (TPE): Process on hold due to new regulation/process will be announced LT can not be defined Process on hold due to new regulation/process will be announced
Note on E92: Liu. Wan (TPE): 1/21 因印度疫情嚴峻及最近他們系統出現問題,所以目前的拿證時間會在延後4-5周, from local: We just had a words with WPC Department and they said that due to some changes on portal (technical issues) all submitted applications are going to take 4-5 more weeks to get the approval.
Note on E93: Liu. Wan (TPE): 1/21 因印度疫情嚴峻及最近他們系統出現問題,所以目前的拿證時間會在延後4-5周, from local: We just had a words with WPC Department and they said that due to some changes on portal (technical issues) all submitted applications are going to take 4-5 more weeks to get the approval.
Note on F99: Liu. Wan (TPE): 1/14-Lockdown from 2021/1/08~2021/02/01
Note on E102: Liu. Wan (TPE): 12/23BV: 12/19~ 01/07 holiday, 更新日期為2020/4/9 估計IFETEL官方放假回來上班後, 案件量會大增, 所以會需要多一點時間讓官方審件 Holiday: 12/19-1/7, IFETEL reviewer預計1/11才會恢復上班
Note on L112: Liu. Raura (TPE): For NPI project put Host level ID
Note on E122: Liu. Wan (TPE): 12/29 The outbreak of Covid- 19 are badly delaying the process, ETA will be delayed from 1/4 to 1/22

## Compare
|  | Carnoustie |  | Montreux
Regulatory P-RTS | RTS | 2021-03-30 |  | 2020-12-29 |  | Happened on Gen 12
| RFD | 2021-03-05 |  | 2020-12-03
|  | Carnoustie | P-RTS days | X12 project | P-RTS days
System Level (Mandatory) | Belarus/Kazakhstan/Russian (CU) | 2021-03-29 | -1 | RTS scope | NA | Andrews 14 CS, Andrews 14 360
| Ukraine (UKSERT) | 2021-05-24 | 55 | 2021-03-03 | 64 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux, Olympic MLK, Andrews 14 CS, Andrews 14 360, Trek 11 CS/360
| South Africa (NRCS) | 2021-04-13 | 14 | 2021-01-14 | 16 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux, Andrews 14 CS, Andrews 14 360, Trek 11 CS/360
| India (BIS) | 2021-04-19 | 20 | 2021-02-25 | 58 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux, Olympic MLK, Andrews 14 CS, Andrews 14 360,
| Chile (SUBTEL) | 2021-04-05 | 6 | 2020-12-30 | 1 | South Peak 14, Montreux,, Andrews 14 CS, Andrews 14 360
| China (NAL) (label impact) | 2021-03-26 | -4 | RTS scope | NA | Request Tablet system approval (NB request only module approval)
| Brazil (ANATEL) | 2021-05-03 | 34 | RTS scope | NA | Request Tablet system approval (NB request only module approval)
| Nigeria (NCC) | 2021-05-17 | 48 | 2021-02-24 | 57 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux, Olympic MLK, Andrews 14 CS, Andrews 14 360
| Zambia (ZICTA) | 2021-04-05 | 6 | 2021-01-13 | 15 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux, Andrews 14 CS, Andrews 14 360
| Ecuador (ARCOTEL) | 2021-05-20 | 51 | RTS scope | NA | Request Tablet system approval (NB request only module approval)
WWLAN Module Level | Taiwan (NCC) | 2021-04-05 | 6 | RTS scope | NA | Andrews 14 CS BSMI ready (3/1) + 5wks
| Philippines (label impact) | 2021-03-08 | -22 | 2020-12-09 | -20 | Olympic MLK, Andrews 14 CS,
System Level (Voluntary) | Taiwan (TGM) | 2021-07-03 | 95 | 2021-07-03 | 186 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux, Olympic MLK, Andrews 14 CS, Andrews 14 360
RFID | Argentina (ENACOM) | 2021-03-29 | -1 | 2021-01-20 | 22 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux, Olympic MLK, Andrews 14 CS, Andrews 14 360, Trek 11 CS/360
| Bahamas (URCA) | 2021-05-20 | 51 | 2021-02-23 | 56 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Dominican Republic (INDOTEL) | 2021-06-03 | 65 | 2021-03-09 | 70 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Guyana (PUC) | 2021-09-09 | 163 | 2021-06-15 | 168 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Haiti (CONATEL) | 2021-05-03 | 34 | 2021-02-24 | 57 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Israel (MoC) | 2021-04-12 | 13 | 2021-02-03 | 36 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Lebanon (TRA/MoT) | 2021-06-15 | 77 | 2021-04-07 | 99 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Moldova (DoC) | 2021-04-05 | 6 | 2021-01-27 | 29 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Mexico (IFETEL) (label impact) | 2021-03-12 | -18 | 2021-01-03 | 5 | South Peak 14, Montreux
| Nicaragua (TELCOR) | 2021-04-06 | 7 | 2021-01-27 | 29 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Paraguay (CONATEL) | 2021-04-06 | 32 | 2021-01-27 | 29 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| Saint Lucia (NTRC) | 2021-04-19 | 45 | 2021-02-10 | 43 | South Peak 14, South Peak 13 CS/360, South Peak 15/15P, Montreux
| South Africa (ICASA) | 2021-04-26 | 52 | 2021-02-17 | 50 | South Peak 14, Montreux

## S&G&E_DVT1_Schedule (hidden)
Carnoustie
Program Status | 1. Carnoustie CSTL v1.0_1 2. Carnoustie 13 schedule_X07a 2. Chinese new year: 2021/2/11-2021/2/16
Regulatory model name | T04H |  | RFD Date: | 2021-03-05 | System CE SAR (excluding WWAN): | 2021-01-11
Regulatory Type name | T04H001 |  | ODM RTS Date: | 2021-03-30 | System CE SAR(including WWAN): | 2021-01-25
Marketing model name (for China WLAN) (for China WWAN) | Latitude 7320 Detachable Latitude 7320-01 Detachable |  | RTO Date: | 2021-03-30 | Korea SAR: | 2021-02-08
Marketing model name (for WW) | Latitude 7320 Detachable |  | Safety Engineer: | Renee Chu | QSG Release Date: | 2021-01-22
|  |  | EMC Engineer: | Ian Chien
Project code #: | FDB33 |  | Green Engineer: | Alfor Liao
Testing/ Verifaction | Sample ETA to LKE | Start | End | Comments
EVT1 | 2020-07-15 | 2020-07-15 | 2020-07-29 | TR on 6/17, need to provide report to ME before TR for solution adding
DVT1 | 2020-10-05 | 2020-10-05 | 2020-10-26
DVT2 | 2021-01-12 | 2021-01-12 | 2021-02-02
PVT | 2021-03-18 | -- | --
BOM Lock Down Plan | Start | End
BOM lock Down | 2021-01-12 | 2021-01-26
Label Turn A Plan | A00 | A01
Label | 2021-02-26 | TBD
Region | Duration (day) | Submitted Date | Target date | Complete | Status | Owner | RDOC Cert. | RDOC Report
Americas
FCC Report | 7 | 2020-12-07 | 2020-12-14 |  |  | EMC
USA/CANADA (UL 62368-1 3ed) | 42 | 2021-02-01 | 2021-03-22 |  |  | Safety
Mexico (NOM) | 35 | 2021-01-22 | 2021-02-26 |  |  | Safety
Brazil (INMETRO) | 49 | -- | N/A |  | Tablet is out of scope. | Green
ENV0379 Report | -- | -- | 2021-02-26 |  |  | Green
USA (Energy Star 8.0) | 30 | 2021-03-25 | 2021-02-26 |  |  | Green
CEC (MEPS) | -- | -- | N/A |  | Tablet is out of scope. | Green
USA (EPEAT-2018) | 28 | 2021-03-25 | 2021-02-26 |  |  | Green
USA (BCS/ DOE/ NRCan) | 42 | 2021-01-15 | 2021-02-26 |  |  | Green
Mexico (MEL) | -- | -- | N/A |  | Tablet is out of MEL scope. | Green
Europe & Middle East
CE Report (EN55022 and EN55032) | 42 | 2020-10-26 | 2020-12-07 |  | Panel issue is to be confirmed. Awaiting the CT comment. We have not submit yet and will update by next week. | EMC
EN301489 | 49 | 2020-10-26 | 2020-12-14 |  | Panel issue is to be confirmed. Awaiting the CT comment. We have not submit yet and will update by next week. | EMC
CB (60950-1) | 49 | 2020-10-26 | 2020-12-14 |  |  | Safety
CB (62368-1 3rd edition) | 84 | 2020-11-09 | 2021-02-01 |  |  | Safety
NEMKO | 7 | 2021-02-08 | 2021-02-15 |  |  | Safety
DELL EMC DoC | 7 | 2021-02-01 | 2021-02-08 |  |  | DELL
Germany (TUVRh-GS or EN62368-1 3ed ) | 42 | 2021-02-01 | 2021-03-22 |  |  | Safety
UAE RoHS | 42 | 2021-01-19 | 2021-03-02 |  |  | Green
UAE (LVE) | 42 | 2021-02-01 | 2021-03-22 |  | Need to wait CB (62368-1) ready for the submission | Safety
Israel Package |  | -- | 2021-02-26 |  |  | Safety
Serbia (KVALITET) | 56 | 2021-02-08 | 2021-03-29 |  |  | Safety
Ukraine (TEC+NSoC+RoHS) | 70 | 2021-03-08 | 2021-06-07 |  | Consider New RFID | Safety
Belarus/Kazakhstan/Russian (CU) | 98 | 2021-02-08 | 2021-05-17 |  | DELL Russia need to release FSS code before submit date | Safety
EAEU RoHS | 42 | 2021-01-19 | 2021-03-02 |  |  | Green
Uzbekistan | 49 | 2021-02-08 | 2021-03-29 |  |  | Safety
Moldova | 56 | 2021-02-08 | 2021-03-29 |  |  | Safety
Saudi Arabia (SASO) | DELL Own | -- | 2021-02-26 |  |  | DELL
South Africa (NCRS) | 134 | 2020-12-14 | 2021-04-27 |  |  | Safety
Kenya(KEBS) | DELL Own | -- | 2021-02-26 |  |  | DELL
Kuwait (KUKAS) | DELL Own | -- | 2021-02-26 |  |  | DELL
Nigeria(SONCAP) | DELL Own | -- | 2021-02-26 |  |  | DELL
Algeria | DELL Own | -- | 2021-02-26 |  |  | DELL
Ethiopia | DELL Own | -- | 2021-02-26 |  |  | DELL
Tanzania | DELL Own | -- | 2021-02-26 |  |  | DELL
Uganda | DELL Own | -- | 2021-02-26 |  |  | DELL
TCO Gen8 | 28 | 2021-03-01 | 2021-03-29 |  |  | Green
Asia Pacific (APJ)
JAPAN (VCCI) | 14 | 2020-12-07 | 2020-12-21 |  |  | EMC
Taiwan (BSMI) | 42 | 2020-12-14 | 2021-02-22 |  |  | EMC/Safety
Taiwan (TGM) | 100 | 2021-03-30 | 2021-07-08 |  | Volumtary Certification, not RTS gating item. Need to confirm BSMI certificate and service manual (RTS) + TWN/EDF(100 days) | Green
China (CCC) | 42 | 2020-12-14 | 2021-02-08 |  |  | Safety
China (CEL) | 30 | 2021-01-19 | 2021-02-18 |  |  | Green
China (CECP) | -- | -- | Per ESPL wish list to do |  | Per ESPL wish list to do (P-RTS)(For China government bid only) | Green
China (CEC) | -- | -- | Per ESPL wish list to do |  | Per ESPL wish list to do (P-RTS)(For China government bid only) | Green
India (BIS) | 98 | 2021-01-11 | 2021-04-19 |  | Schedule is based on Battery pack BIS ready before 2021/1/11 | Safety
India (BEE Star) | -- | -- | N/A |  |  | Green
South Korea (Safety-KC) | 35 | 2020-12-14 | 2021-02-01 |  |  | Safety
South Korea (EMC-KC report) | 42 | 2020-12-07 | 2021-01-18 |  |  | EMC
South Korea (EMC-KC certificate) | 14 | 2021-02-08 | 2021-02-22 |  | Initial cert need to wait KC-SAR done | EMC
South Korea (eStandby) | 30 | -- | N/A |  | Tablet is out of scope. | Green
South Korea (Eco-Label) | DELL Own | -- | N/A |  |  | DELL
Vietnam EMC Report | 42 | 2020-12-14 | 2021-01-25 |  |  | EMC
Vietnam MEPS Report | 56 | 2021-02-01 | 2021-03-29 |  |  | Green
Australia/New Zealand
MEPS | 30 | -- | N/A |  |  | Green
RCM Report | 7 | 2020-12-07 | 2020-12-14 |  |  | EMC
This schedule is base on :
System and adapter sample arrive on |  |  | 2020-10-05 |  | Carnoustie battery Safety NOA |  | BYD | SMP | SWD
DELL LoA |  |  | 2020-10-05 |  |  | UL2054/UL62368 | 2020-10-19 | 2020-10-19 | 2020-10-19
DELL EMC DoC ready on (English) |  |  | 2020-12-14 |  |  | CB60950/CB62133/CB62368 | 2020-10-19 | 2020-10-19 | 2020-10-19
DELL EN62311 DoC and RF related Documents |  |  | 2020-12-14 |  |  | CE | 2020-10-26 | 2020-10-26 | N/A
User's manual and rating label in English |  |  | 2020-10-05 |  |  | TUV60690/TUV62368 | 2020-10-26 | 2020-10-26 | 2020-10-26
User's manual with Other language T-Chinese, S-Chienese, Russian, Hebrew, Korea, Spanish, Serbian, Portuguese |  |  | 2020-10-26 |  |  | PSE | 2020-10-26 | 2020-10-26 | 2020-10-20
Key part cert. & report ready (ex. Adapter/Batterypack…etc): CB |  |  | 2020-10-19 |  |  | TISI | 2020-10-19 | 2020-10-19 | Done
Key part cert. & report ready (ex. Adapter/Batterypack…etc): Others |  |  | 2020-12-14 |  |  | KC | 2020-11-02 | 2020-11-02 | 2020-11-22
Acoustic report ready |  |  | N/A |  |  | GOST | 2020-11-02 | 2020-11-02 | 2020-11-02
BSMI授權進口書(if needed) |  |  | 2021-02-22 |  |  | BSMI | 2020-11-02 | 2020-11-15 | 2020-11-02
[6 empty] | GB31241 | 2020-11-09 | 2020-11-09 | 2020-11-09
Certificate color code | [5 empty] | VN IEC 62133 | 2020-11-09 | 2020-11-09 | 2020-11-09
before RFD | [5 empty] | BIS (62133-2:2017) | 2021-01-11 | 2021-01-11 | 2021-01-11
Between RFD and RTS
After RTS before RTO, please set restriction
After RTO, please set restriction
Completed
Formulas:
Start = [FDB33]
Start = [Green Engineer:]-[FDB33]
Green Engineer: = [Start]+14
Green Engineer: = [Start]+[FDB33]
FDB33 = [Start]-14

## RF Schedule DVT1 (hidden)
Carnoustie (Portable Computer - Tablet) | [5 empty] | Schedule ver. Carnoustie 13 schedule_X07a | [6 empty] | Antenna Filing |  |  | NCC Photo Filing (after RTO)
CG | SPT | Min. ant-to-body distance | XXmm | RMN | T04H | DVT1.0 Sample ETA | 2020-10-05 | Safety CB Report/Cert | 2021-02-01 | Label Turn A | 2021-03-17 |  | Module | Antenna Cycle | Actual Submitted Date | Antenna Cycle | Actual Submitted Date
Project Code | (APR)FDB33 | RF module | WLAN/BT 1. AX201D2W RFID: DWRFID2002 WWAN: T77W968 (DW5821e, CAT16, Darwin 1.0) | RTN | T04H001 | DVT1.0 Regulatory Sample for RFID (+6wks) | 2020-11-16 | EMC EN 301489 | 2020-12-14 | RFD Date | 2021-03-24 |  | AX210
RF RD | Lee. IvanSH |  |  | MMN-WLAN | Latitude 7320 Detachable | DVT1.0 Regulatory Sample for WLAN (+6wks) | 2020-11-16 | BSMI Report/Cert | 2021-02-22 | RTS Date | 2021-04-19 |  | AX210_FCC/CE report ready |  | 2020-12-31 | 12/4~2021/2/5
RF Lab | BV-ADT |  |  | MMN-WWAN | Latitude 7320-01 Detachable | DVT1.0 Regulatory Sample for WWAN (+8wks) | 2020-11-30 | A Rev Driver |  | RTO Date | 2021-04-19 |  | AX210_JP/KR/China |  | 2021-02-05
RF Reg. Engineer | Miya Lan |  |  |  |  | DVT1.1 Sample ETA | 2020-11-09 | DVT1.1 Regulatory Sample (+6wks) | 2020-11-30 |  |  |  | AX210_Malaysia |  | 2021-04-08 | 2/25~4/8
Country | Type Approval | Module | Start Date | L/T | Target Date | Status Summary | Actual Start | Actual Completion | Reg. Model Name | Label Requirement | RDOC Cert. | RDOC Report
SAR
EU | EN 50566/EN 62209 | AX201 | 2020-11-16 | 56 | 2021-01-11 |  |  |  | RMN |  |  | V (Date)
|  | T77W968 | 2020-11-30 | 56 | 2021-01-25 |  |  |  | RMN |  |  | V (Date)
Australia | AS/NZS 2772.2:2011 | AX201 | 2020-11-16 | 56 | 2021-01-11 | same as CE |  |  | RMN |  |  | V (Date)
|  | T77W968 | 2020-11-30 | 56 | 2021-01-25 | same as CE |  |  | RMN |  |  | V (Date)
US/Canada | SAR+Review | AX201 | 2020-11-16 | 77 | 2021-02-01 |  |  |  | RMN |  | V (Date) | V (Date)
| SAR | T77W968 | 2020-11-30 | 56 | 2021-01-25 |  |  |  | RMN |  |  | V (Date)
| Review |  | 2021-01-25 | 21 | 2021-02-15 |  |  |  | RMN
Korea | KC SAR | AX201 | 2020-11-16 | 70 | 2021-01-25 |  |  |  | RTN |  |  | V (Date)
|  | T77W968 | 2020-11-30 | 70 | 2021-02-08 |  |  |  | RTN |  |  | V (Date)
Japan | SAR | T77W968+AX201 | 2020-11-30 | 56 | 2021-01-25 |  |  |  | RTN | (IDV) R: 020-200034 5GHz band (W52,W53): Indoor use only (except communicate to high power radio) | V (Date) | V (Date)
| Review |  | 2021-01-25 | 14 | 2021-02-08 |  |  |  | RTN
System Approval
Argentina | ENACOM | RFID | 2020-11-16 | 133 | 2021-03-29 |  |  |  | RMN |  | V (Date)
Azerbaijan | ARRVITN | All modules | 2021-01-25 | 56 | 2021-03-22 |  |  |  | RMN |  | V (Date)
Belarus | DoC (CIT+PCP+CDT) | AX201 | 2021-01-11 | 70 | 2021-03-22 |  |  |  | RMN | (WW) TP Logo | V (Date)
Brazil | ANATEL Class 2 (CIT+PCP+CEB+CDT) | AX201(+RFID) | 2020-11-16 | 154 | 2021-04-19 |  |  |  | RMN | (IDV) ANATEL: 01432-20-01643 | V (Date)
| ANATEL Class 1 (CIT+PCP+CEB+CDT) | AX201+T77W968 (+RFID) | 2020-11-30 | 154 | 2021-05-03 | Adapter for 60W -DVT1 sample Delta: 12 -DVT2 early sample demand before 10/12 Liteon: 24 Chicony: 24 2020/7/30: Ask additional adapter sample, PJE inform 40W & 65W ok, 60W adapter need checking (ETA: 10/E, EMC recommend use Early sample for Liteon/ Chicony, and hightlight to CT if testing fail) |  |  | RMN | (IDV) ANATEL: 01431-20-01643 | V (Date)
Chile | RSE | AX201 | 2020-11-16 | 28 | 2020-12-14 |  |  |  | RMN |  | V (Date)
| SUBTEL |  | 2021-01-11 | 84 | 2021-04-05 |  |  |  | RMN
China | SRRC (WLAN) | AX201 | 2020-11-16 | 10 | 2020-11-26 | (文件&寄樣) |  |  | MMN-WLAN | (COO) CMIIT ID: 2020AP1077 | V (Date)
|  |  | 2020-11-26 | 18 | 2020-12-14 | (受理&排測)
|  |  | 2020-12-14 | 21 | 2021-01-04 | (測試)
|  |  | 2021-01-04 | 35 | 2021-02-08 | (審理&取證)
| SRRC (WWAN) | T77W968+AX201 | 2020-11-30 | 10 | 2020-12-10 | (文件&寄樣) |  |  | MMN-WWAN | (COO) CMIIT ID: 2019CPXXXX | V (Date)
|  |  | 2020-12-10 | 18 | 2020-12-28 | (受理&排測)
|  |  | 2020-12-28 | 21 | 2021-01-18 | (測試)
|  |  | 2021-01-18 | 35 | 2021-02-22 | (審理&取證)
| NAL (CIT) | T77W968+AX201 | 2020-11-30 | 116 | 2021-03-26 | China Holiday:2/11~2/17 Booking Intel TW lab for WAPI pre-test with Intel FAE Frank.(refer to Augusta MLK's mail) 8/31: Inquire Intel about booking lab for WAPI pre-test. 9/3: Intel suggest to wait till TGL PV is ready for test. Suggest to test it after ww42 timeframe.--> Check with RF RD |  |  | MMN-WWAN | Mii label | V (Date)
| NAL (CTY) | T77W968+AX201 | 2020-11-30 | 116 | 2021-03-26 |  |  |  |  | Mii label | V (Date)
| NAL (CDT) | T77W968+AX201 | 2020-11-30 | 116 | 2021-03-26 |  |  |  |  | Mii label | V (Date)
Ecuador | ARCOTEL | AX201+RFID | 2021-04-19 | 56 | 2021-06-14 | Wait FCC grant |  |  |  |  | V (Date)
Indonesia | SDPPI (Taiwan) |  | N/A | N/A | N/A | Indonesia not in tablet CSTL. |  |  | RMN | XXXXX/SDPPI/2020 5100 | V (Date)
| SDPPI (China) |  | N/A | N/A | N/A | Indonesia not in tablet CSTL. |  |  |  | XXXXX/SDPPI/2020 5100 | V (Date)
Jordan | TRC (RTN) | AX210+RFID+T77W968 | 2021-01-25 | 56 | 2021-03-22 |  |  |  | RTN
Korea | USIM report | T77W968 | 2020-11-30 | 35 | 2021-01-04 |  |  |  | RTN
Malaysia | MCMC | All modules | 2021-02-01 | 42 | 2021-03-15 |  |  |  | RMN | (WW) MCMC Logo | V (Date)
Morocco | ANRT | All modules | 2021-01-25 | 42 | 2021-03-08 |  |  |  | RMN | (WW) N°D’AGRÉMENT MR 22607 ANRT 2020 (28/01/2020) | V (Date)
Nigeria | NCC (Latitude 9510) | All modules | 2021-01-25 | 112 | 2021-05-17 |  |  |  | MMN | (UM) compliacne statement | V (Date)
Peru | MTC (Ministry of Transportation and Communications) | All modules | 2021-01-25 | 42 | 2021-03-08 | Draft status of bulletin. Still waiting for Dell approval 9/16: 1. ADT reply L/T is 5~6wks and provide Checking list. 2. Still waiting for ADT deal contract price with Dell.
Philippines | NTC | AX201 | 2021-01-11 | 42 | 2021-02-22 |  |  |  | RMN+MMN |  | V (Date)
|  | AX201+RFID | 2021-01-11 | 42 | 2021-02-22
|  | AX201+T77W968 | 2021-01-25 | 42 | 2021-03-08 |  |  |  |  | (IDV) ESD-GEC-2005903 | V (Date)
|  | AX201+RFID+T77W968 | 2021-01-25 | 42 | 2021-03-08 |  |  |  |  | (IDV) ESD-GEC-2005903
Thailand | SDoC | AX201 | 2021-01-11 | 35 | 2021-02-15 |  |  |  | RMN |  | V (Date)
| Class B | T77W968+AX201 | 2021-01-25 | 42 | 2021-03-08 |  |  |  | RMN | (IDV) NBTC: B38084-20-0591 | V (Date)
Taiwan | Conducted power report | T77W968 | 2020-11-30 | 35 | 2021-01-04 |  |  |  | RMN
| NCC add host |  | 2021-02-22 | 35 | 2021-03-29 | [5 empty] | V (Date)
Zambia | ZICTA | All modules |  | 70 |  | 7/27: Bulletin-Zambia own by local distributor. 7/30: Compal ID have removed Zambia label from label plan. |  |  |  | (IDV) ZMB/ZICTA/TA/2020/2/40 | V (Date)
RFID Limited Module Approval
EU | 1. EN300330 2. EN301489 -1/-3 3. EN60950 4. EN62311 DoC | RFID | 2020-11-16 | 28 | 2020-12-14 |  |  |  | RFID: DWRFID2002 | CE | V (Date) | V (Date)
Australia | AS/NZS 4268:2017 MPE | RFID | 2020-11-16 | 28 | 2020-12-14 |  |  |  |  | RCM with R-NZ |  | V (Date)
US | FCC Part 15C+New ID | RFID | 2020-11-16 | 42 | 2021-03-17 |  |  |  |  | Contains FCC ID: E2K-DWRFIDXXXX | V (Date) | V (Date)
Canada | IC RSS 210+New ID | RFID | 2020-11-16 | 42 | 2020-12-28 |  |  |  |  | Contains IC: 1514B-DWRFIDXXXX | V (Date) | V (Date)
Japan | Extremely low power report | RFID | 2020-11-16 | 35 | 2020-12-21 | [6 empty] | V (Date)
Korea | Radio-Telecom test for RFID | RFID | 2020-11-16 | 42 | 2020-12-28 | [6 empty] | V (Date)
Taiwan | NCC LP0002+Cert (5*adatper) | RFID | 2020-11-16 | 42 | 2020-12-28 |  |  |  |  | XXXX | V (Date) | V (Date)
RFID WW Approval
Antiqua And Barbuda | MBT | RFID | 2020-12-14 | 42 | 2021-01-25 |  |  |  | RFID: DWRFID2002 |  | V (Date)
Armenia | ANAB | RFID | 2020-12-14 | 28 | 2021-01-11 |  |  |  |  | ANAB compliance Mark (Voluntary) | V (Date)
Aruba | DTZ | RFID | 2020-12-14 | 63 | 2021-02-15 | [5 empty] | V (Date)
Bahamas | URCA | RFID | 2021-04-19 | 56 | 2021-06-14 | Wait FCC grant |  |  |  |  | V (Date)
Bahrain | iGA | RFID | 2020-12-14 | 42 | 2021-01-25 | [5 empty] | V (Date)
Barbados | TU | RFID | 2020-12-14 | 28 | 2021-01-11 | [5 empty] | V (Date)
Belize | PUC | RFID | 2020-12-14 | 56 | 2021-02-08 | [5 empty] | V (Date)
Bolivia | ATT | RFID | 2020-12-14 | 98 | 2021-03-22 | [5 empty] | V (Date)
Botswana | BOCRA | RFID | 2020-12-14 | 49 | 2021-02-01 |  |  |  |  | BOCRA REGISTERED No : BOCRA/TA/2019/4316 | V (Date)
Cambodia | MPTC (Taiwan+China) | RFID | 2020-12-14 | 35 | 2021-01-18 | [5 empty] | V (Date)
Costa Rica | SUTEL | RFID | 2020-12-14 | 35 | 2021-01-18 | [5 empty] | V (Date)
Cote D'ivoire | ARTCI | RFID | 2020-12-14 | 84 | 2021-03-08 | [5 empty] | V (Date)
Dominica | NTRC | RFID | 2020-12-14 | 84 | 2021-03-08 | [5 empty] | V (Date)
Dominican Republic | INDOTEL | RFID | 2021-04-19 | 70 | 2021-06-28 | Wait FCC grant |  |  |  |  | V (Date)
Egypt | NTRA | RFID | 2020-12-14 | 56 | 2021-02-08 | [5 empty] | V (Date)
Eswatini (舊名 Swaziland) | SCCOM | RFID | 2020-12-14 | 56 | 2021-02-08 | [5 empty] | V (Date)
Fiji | TAF | RFID | 2020-12-14 | 46 | 2021-01-29 | [5 empty] | V (Date)
Ghana | NCA | RFID | 2020-12-14 | 49 | 2021-02-01 |  |  |  |  | NCA APPROVED: SRO-1M-7E4-X17 | V (Date)
Grenada | NTRC | RFID | 2020-12-14 | 70 | 2021-02-22 | [5 empty] | V (Date)
Guyana | PUC | RFID | 2021-04-19 | 168 | 2021-10-04 | Wait FCC grant |  |  |  |  | V (Date)
Haiti | CONATEL | RFID | 2020-12-14 | 140 | 2021-05-03 | [5 empty] | V (Date)
India | DoT (China) | RFID | 2020-12-14 | 49 | 2021-02-01 | [5 empty] | V (Date)
| DoT (Taiwan) | RFID | 2020-12-14 | 49 | 2021-02-01 | [5 empty] | V (Date)
Israel | MoC | RFID | 2020-12-14 | 119 | 2021-04-12 | [5 empty] | V (Date)
Jamaica | SMA | RFID | 2020-12-14 | 49 | 2021-02-01 | [5 empty] | V (Date)
Kiribati | CCK | RFID | 2020-12-14 | 70 | 2021-02-22 | [5 empty] | V (Date)
Kuwait | CITRA | RFID | 2020-12-14 | 71 | 2021-02-23 | [5 empty] | V (Date)
Lao, People'S Democratic Republic | MPT | RFID | 2020-12-14 | 42 | 2021-01-25 | [5 empty] | V (Date)
Lebanon | TRA/MoT | RFID | 2020-12-14 | 183 | 2021-06-15 | [5 empty] | V (Date)
Malawi | MACRA | RFID | 2020-12-14 | 60 | 2021-02-12 | [5 empty] | V (Date)
Malaysia | MCMC | RFID | 2020-12-14 | 56 | 2021-02-08 | [5 empty] | V (Date)
Mexico | IFETEL | RFID | 2020-12-14 | 88 | 2021-03-12 |  |  |  |  | IFT No. RCPDEDWXX-XXXX | V (Date)
Moldova | DoC (CIT+PCP+CDT) | RFID | 2020-12-14 | 112 | 2021-04-05 |  |  |  |  | SM Mark + cert. body no. (024) | V (Date)
Mongolia | CRC (Taiwan+China) | RFID | 2020-12-14 | 56 | 2021-02-08 | [5 empty] | V (Date)
Nicaragua | TELCOR | RFID | 2020-12-14 | 113 | 2021-04-06 | [5 empty] | V (Date)
Oman | TRA + authorization | RFID | 2020-12-14 | 42 | 2021-01-25 |  |  |  |  | OMAN - TRA TRA/TA-R/8971/20 D100428 | V (Date)
Panama | ASEP | RFID | 2020-12-14 | 70 | 2021-02-22 | [5 empty] | V (Date)
Papua New Guinea | NICTA | RFID | 2020-12-14 | 49 | 2021-02-01 | [5 empty] | V (Date)
Paraguay | CONATEL | RFID | 2020-12-14 | 113 | 2021-04-06 |  |  |  |  | (on USH) NR: XXXX-XX-X-XXXX | V (Date)
Saint Kitts And Nevis | NTRC | RFID | 2020-12-14 | 84 | 2021-03-08 | [5 empty] | V (Date)
Saint Lucia | NTRC | RFID | 2020-12-14 | 126 | 2021-04-19 | [5 empty] | V (Date)
Saudi Arabia | CITC | RFID | 2020-12-14 | 42 | 2021-01-25 | 9/3: RF reg. Wayne. Lu inform Dell Jack Saudi Arabia is no longer accept WLAN/RFID module certification, it must go through system approval no matter NB or Tablet |  |  |  | TA xxxx-y CITC E-Label | V (Date)
Senegal | ARTP | RFID | 2020-12-14 | 70 | 2021-02-22 | [5 empty] | V (Date)
Serbia | KVALITET | RFID | 2020-12-14 | 46 | 2021-01-29 |  |  |  |  | Ratel mark (XXXX YY) | V (Date)
Singapore | iMDA | RFID | 2020-12-14 | 14 | 2020-12-28 |  |  |  |  | This device contains DWRFIDXXXX module. Complies with iMDA standards DA104808 | V (Date)
Solomon Islands | TCSI | RFID | 2020-12-14 | 84 | 2021-03-08 | [5 empty] | V (Date)
South Africa | ICASA | RFID | 2020-12-14 | 133 | 2021-04-26 |  |  |  |  | (IDV) ICASA label | V (Date)
Suriname | TAS | RFID | 2020-12-14 | 56 | 2021-02-08 | [5 empty] | V (Date)
Tanzania | TCRA | RFID | 2020-12-14 | 49 | 2021-02-01 | [5 empty] | V (Date)
Tunisia | CERT | RFID | 2020-12-14 | 60 | 2021-02-12 | [5 empty] | V (Date)
UAE | TRA | RFID | 2020-12-14 | 42 | 2021-01-25 |  |  |  |  | TRA REGISTERED No: ER78629/20 DEALER No: 0032863/10 | V (Date)
Uruguay | URSEC | RFID | 2020-12-14 | 21 | 2021-01-04 | [5 empty] | V (Date)
Venezuela | CONATEL | RFID | 2020-12-14 | 35 | 2021-01-18 | [5 empty] | V (Date)
Vietnam | report only RF-EMC (QCVN96) RF (QCVN55) | RFID | 2020-12-14 | 42 | 2021-01-25 | [5 empty] | V (Date)
Zimbabwe | POTRAZ | RFID | 2020-12-14 | 84 | 2021-03-08 | [6 empty] | V (Date)
Formulas:
Start Date = [Target Date, row above]
Target Date = [Start Date]+[L/T]
Target Date = SUM([Start Date]:[L/T])
Note on J4: Su. CindyHC (TPE): For WWAN NCC add host CNS 13438 EMC CNS 14336 Safety
Note on K6: Liu. Raura (TPE): RD pull in 6wks to 3wks for WWAN 2 source
Note on B62: Huang. Elaine (TPE): Approval is exempted if Field Strength is < 500uV/m @ 3m

## Post-RTS (DVT1) (hidden)
P-RTS country (Mandatory):
Project | RTS | Regulatory | Country | Certificate | Lead Time | Schedule | Remark | Category | Labeling impact
Carnoustie | 2021-03-30 | Safety | Ukraine | TEC+NSoC+RoHS | 70 | 2021-06-07 | Consider New RFID | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-03-30 | Safety | Belarus/Kazakhstan/Russian | CU | 98 | 2021-05-17 |  | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-03-30 | Safety | South Africa | NCRS | 134 | 2021-04-27 |  | Host | N/A (only has module label)
Carnoustie | 2021-03-30 | Safety | India | BIS | 98 | 2021-04-19 | Schedule is based on Battery pack BIS ready before 2021/1/11 | Host | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | RF | Brazil | ANATEL | 154 | 2021-05-03 | Sample ready on 2020/11/30 + 22wks | Host_WWAN | Yes
Carnoustie | 2021-04-19 | RF | Chile | SUBTEL | 112 | 2021-04-05 | Sample ready on 2020/11/16+ 16wks | Host | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | China | NAL | 116 | 2021-03-26 | Sample ready on 2020/11/30 + 16.6wks China Holiday:2/11~2/17 | Host | Yes
Carnoustie | 2021-04-19 | RF | Ecuador | ARCOTEL | 56 | 2021-06-14 | Wait for FCC grant on 3/25 + 8wks | Host | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Nigeria | NCC | 112 | 2021-05-17 | CE SAR ready (2021/1/25) + 16wks | Host | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Philippines | NTC | 42 | 2021-03-08 | CE SAR ready (2021/1/25) + 16wks | Host_WWAN | Yes
Carnoustie | 2021-04-19 | RF | Taiwan (WWAN) | NCC | 35 | 2021-03-29 | BSMI ready (2021/3/1)+ 5wks | Host_WWAN | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Argentina (RFID) | ENACOM | 133 | 2021-03-29 | Sample ready on 2020/11/16 + 19wks | RFID | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | RF | Bahamas (RFID) | URCA | 56 | 2021-06-14 | Wait for FCC grant on 3/25 + 8wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Dominican Republic (RFID) | INDOTEL | 70 | 2021-06-28 | Wait for FCC grant on 3/25 + 10wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Guyana (RFID) | PUC | 168 | 2021-10-04 | Wait for FCC grant on 3/25 + 24wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Haiti (RFID) | CONATEL | 140 | 2021-05-03 | CE EMC ready (2020/12/14)+ 20wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Israel (RFID) | MoC | 119 | 2021-04-12 | CE EMC ready (2020/12/14)+ 17wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Lebanon (RFID) | TRA/MoT | 183 | 2021-06-15 | CE EMC ready (2020/12/14)+ 26wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Mexico (RFID) | IFETEL | 88 | 2021-03-12 | CE EMC ready (2020/12/14)+ 12.6wks | RFID | Yes
Carnoustie | 2021-04-19 | RF | Moldova (RFID) | DoC | 112 | 2021-04-05 | CE EMC ready (2020/12/14)+ 16wks | RFID | No (can be ready first, set restriction until certification ready)
Carnoustie | 2021-04-19 | RF | Nicaragua (RFID) | TELCOR | 113 | 2021-04-06 | CE EMC ready (2020/12/14)+ 16wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | Paraguay (RFID) | CONATEL | 113 | 2021-04-06 | CE EMC ready (2020/12/14)+ 16wks | RFID | Yes (RFID antenna)
Carnoustie | 2021-04-19 | RF | Saint Lucia (RFID) | NTRC | 126 | 2021-04-19 | CE EMC ready (2020/12/14)+ 18wks | RFID | N/A (no label requirement)
Carnoustie | 2021-04-19 | RF | South Africa (RFID) | ICASA | 133 | 2021-04-26 | CE EMC ready (2020/12/14)+ 19wks | RFID | Yes
Carnoustie | 2021-04-19 | RF | Zambia | ZICTA | 70 |  | Zambia own by local distributor | Host | Yes
P-RTS Country (Voluntary):
Project | RTS | Regulatory | Country | Certificate | Lead Time | Schedule | Remark
Carnoustie | 2021-03-30 | Green | Taiwan | TGM | 100 | 2021-07-08 | Volumtary Certification, not RTS gating item. Need to confirm BSMI certificate and service manual (RTS) + TWN/EDF(100 days)
Carnoustie | 2021-03-30 | Green | China | CECP | -- | Per ESPL wish list to do | For China purchase case
Carnoustie | 2021-03-30 | Green | China | CEC | -- | Per ESPL wish list to do | For China purchase case
Aligned with GOE, Label is post-FRC item, but can be RTS scope
Project | RTS | Regulatory | Country | Certificate | Lead Time | Schedule | Remark | Category | Labeling impact